## OUTPUT Amendment Summary - V2
Program | Project Title | TIP ID | Location | Existing Funding ($M) | Proposed Funding ($M) | Funding Difference ($M) | Old Start Year (FFY) | New Start Year (FFY) | RIDOT's Justification for Proposed Change
Pavement Capital Program | Improvement to Nayatt Rd (Formerly: "Nyatt Rd (Rumstick Rd to Washington Rd)") | 1296 | Barrington | 3.55 | 3.55 | 0 | 2018 | 2018 | Altering funding for this line item to meet the needs of the project. RIDOT has determined that this project can be completed with a reduction in funding. In addition, the project name is changing to match the RhodeWorks Quarterly Report.
Pavement Capital Program | Rt 103/114, County Rd (Federal Rd to Barrington Bridge) | 1297 | Barrington | 2.2 | 4.02 | 1.82 | 2023 | 2023 | The budget for this line item is being altered to meet the needs of the project.
Transportation Alternatives | East Bay Bike Path Bridge Replacement (Barrington River and Warren Bridges) | 5005 | Barrington | 10.4 | 10.4 | 1e-08 | 2022 | 2019 | Project advanced due to condition of the structures.
Transportation Alternatives | Safe Routes to School Infrastructure Improvements for Barrington Middle School | 5001 | Barrington | 0.336 | 0.34 | 0.004 | 2018 | 2018 | Project advanced by RIDOT to construction
Transportation Alternatives | Safe Routes to School Infrastructure Improvements for Primrose Elementary School | 5002 | Barrington | 0.384 | 0.38 | -0.004 | 2018 | 2018 | Project advanced by RIDOT to construction.
Pavement Capital Program | Rt 103, Willet Ave (Bullocks Point Ave to Wamponoag Ave) | 1298 | Barrington, East Providence | 4.2 | 6.73 | 2.53 | 2024 | 2024 | The budget for this line item is being alterered to meet the needs of the project.
Pavement Capital Program | Rt 114, Wampanoag Trail (East Shore Expressway to Federal Rd) | 1290 | Barrington, East Providence | 7.4 | 7.4 | 0 | 2022 | 2024 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability.
Bridge Capital Program | Bridge Group 15A | 17 | Barrington, East Providence, Warren | 7.8 | 7.9 | 0.1 | 2018 | 2018 | The funding sources for this line item are being altered in this Amendment.
Bridge Capital Program | Bridge Group 44A | 257 | Bristol | 4 | 4 | 0 | 2018 | 2018 | The cash flow for this line item is being adjusted to meet the needs of the project. There is no budgetary or scheduling change to this line item.
Pavement Capital Program | Route 114 Hope Street and Ferry Road (Metacom Ave at RWU to Constitution St) | 1299 | Bristol | 1.55 | 2.65 | 1.1 | 2021 | 2021 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 136, Metacom Ave (Warren T/L to Ferry Road) | 1301 | Bristol | 6.1 | 9.71 | 3.61 | 2023 | 2024 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability.
Transportation Alternatives | Herreshoff Marine Museum | 5007 | Bristol | 0.82 | 0 | -0.82 | 2025 | N/A | This project is being removed from the STIP based on a review of the TAP-qualifying activities in coordination with Statewide Planning. This project is not considered an acceptable Transportation Alternatives project.
Traffic Safety Capital Program | *REMOVED* Intersection Safety Improvements to Warren Avenue, Pawtucket Avenue, and Ferry Road (Formerly: "Intersection Safety Improvements to Warren Avenue, Pawtucket Avenue, and Ferry Road") | 1541 | Bristol, East Providence | 7.3 | 0 | -7.3 | 2022 | N/A | The funding for this line item is being re-allocated to TIP ID 9601 for Statewide Intersection Safety Improvements, where it can be distributed to higher priority safety improvements throughout the state based on locations identified in the HSIP program.
Bridge Capital Program | Bridge Group 44 | 43 | Bristol, East Providence, Jamestown, Portsmouth, Tiverton | 19.5484 | 7 | -12.5484 | 2021 | 2021 | Bridges 012601, 029201, 047701, 049501, 072401, and 115401 are being removed from this line item, along with a portion of the funding supporting this project. Those bridges will shift to other line items in the Bridge Capital Program. Bridge Group 44 will now consist of the following bridges: 020901, 021401, 028901, 011301, and 115301. Removed 012601 Removed 029201 Removed 047701 Removed 049501 Removed 072401 Removed 115401
Bridge Capital Program | Bridge Group 44B | TBD44B | Bristol, East Providence, Jamestown, Portsmouth, Tiverton | 0 | 10.5 | 10.5 | N/A | 2021 | New bridge group. Bridges 012601, 047701, 072401, 115301, 115401, and 049501 are being added to this group, along with funding to meet the needs of the project. This line item will consist of major rehabilitation work, superstructure, and/or total bridge replacement. Added 012601 Added 047701 Added 072401 Added 115301 Added 115401 Added 049501
Pavement Capital Program | Rt 114, Hope St and Main St (Washington St to Dyer Ave) | 1300 | Bristol, Warren | 3.5 | 6.13 | 2.63 | 2022 | 2024 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Traffic Safety Capital Program | Intersection Safety Improvements to Metacom Avenue (RI-136) - SI | 1458 | Bristol, Warren | 0 | 1.4 | 1.4 | N/A | 2018 | Adjusted to include prior year authorization; project now fully funded. (Project limits changes from "" to "RI-136")
Bridge Capital Program | Bridge Group 17B | 236 | Burrillville | 10.82 | 10.8 | -0.02 | 2020 | 2020 | The PTSID for this line item is being corrected and a very minor funding alteration is being made to meet the needs of this project.
Bridge Capital Program | Bridge Group 43A | 231 | Burrillville | 7 | 9.74 | 2.74 | 2019 | 2019 | The funding for this line item is being altered to meet the needs of the project.
Bridge Capital Program | Bridge Group 58B | 196 | Burrillville | 2.3 | 3.17 | 0.87 | 2018 | 2018 | This project reached substantial completion November 15, 2018. The funding for this line item is being adjusted to reflect the needs of the project in its final stages.
Pavement Capital Program | Victory Hwy & Rte 107 East Avenue | 1302 | Burrillville | 3.3 | 3.26 | -0.04 | 2018 | 2022 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability.
Traffic Safety Capital Program | *REMOVED* Safety Corridor Improvements to Route 102 Phase 2 Burrillville - Guardrail and Pedestrian Upgrades (Formerly: "Safety Corridor Improvements to Route 102 Phase 2 Burrillville - Guardrail and Pedestrian Upgrades") | 1526 | Burrillville | 1.3 | 0 | -1.3 | 2021 | N/A | RIDOT has determined that Phase 1 work in this area has reduced crashes along the corridor. RIDOT will continue to monitor traffic safety in the area prior to allocating additional funds to safety improvements in the area. For the time being, this line item may be eliminated.
Bridge Capital Program | Bridge Group 17 | 19 | Burrillville, Cumberland, Lincoln, North Providence, North Smithfield, Smithfield | 8.35 | 8.35 | 0 | 2019 | 2019 | The specific funding sources being used to support this project are shifting. There is no budgetary or scheduling change to this line item.
Pavement Capital Program | Reservoir Rd (South Main St to US-44) | 1304 | Burrillville, Glocester | 1.5 | 3.41 | 1.91 | 2023 | 2025 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this project is being adjusted to meet the estimated needs of the project.
Pavement Capital Program | Rt 7 - Douglas Pike (Whipples Pond to Joslin Rd) | 1578 | Burrillville, North Providence, North Smithfield, Smithfield | 5.25 | 9.6 | 4.35 | 2024 | 2024 | The budget for this line item is being altered to meet the needs of the project.
Bridge Capital Program | Bridge Group 47A | TBD47A | Central Falls | 0 | 3.5 | 3.5 | N/A | 2022 | New bridge group. This bridge group will consist of bridge #091701. Funding is being added to this line item to meet the needs of the project, due to readiness and coordination with railroad. Added 091701
Transportation Alternatives | Blackstone River Bikeway - Segment 3B-1 | 5012 | Central Falls, Cumberland | 1.1 | 0 | -1.1 | 2018 | N/A | Project shifted to Green Economy Bond funding provided by DEM for implementation.
Bridge Capital Program | Bridge Group 24 | 26 | Central Falls, Cumberland, Lincoln, North Providence, Pawtucket | 51.001 | 51.001 | 0 | 2024 | 2024 | Bridge #014501 is being removed from this line item to create Bridge Group 24A. There is no budgetary change to this line item. Removed 014501
Pavement Capital Program | Broad Street Regeneration Project | 9007 | Central Falls, Cumberland, Pawtucket | 16.75 | 16.75 | 0 | 2018 | 2018 | The budget for this line item is being altered to meet the needs of the project.
Bridge Capital Program | Bridge Group 47 | 46 | Central Falls, Lincoln | 17.1396 | 14 | -3.1396 | 2020 | 2020 | Bridge #091701 is being removed from this bridge group and added to the newly created Bridge Group 47A. As a result, the budget for this line item is being reduced. Removed 091701
Pavement Capital Program | Rt. 122/Lonsdale Ave (Dexter St to Cumberland T/L) | 9556 | Central Falls, Lincoln | 6.016 | 6.02 | 0.004 | 2026 | 2025 | This project is being recommended for acceleration due to the condition of pavement in the area.
Pavement Capital Program | Rt 122, Lonsdale Ave (Dexter St to US-1) | 1306 | Central Falls, Pawtucket | 3 | 4.84 | 1.84 | 2023 | 2023 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Improvements to Old Post Road Route 1A, Contract 2 (Formerly: "Rt 1A, Old Post Rd (US-1 to US-1)") | 1308 | Charlestown | 2.15 | 2.5 | 0.35 | 2020 | 2019 | This line item's schedule and budget are being altered to suit the project's operational needs.
Bridge Capital Program | Bridge Group 12 | 14 | Charlestown, Coventry, Cranston, East Greenwich, Hopkinton, Richmond, Warwick, West Greenwich, West Warwick, Westerly | 14.01 | 11.36 | -2.65 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project. RIDOT has determined that a reduction in funding will still leave this project with enough support to be completed.
Bridge Capital Program | Bridge Group 45 | 44 | Charlestown, Exeter, Hopkinton, Richmond, Westerly | 7.199 | 7.199 | 0 | 2026 | 2026 | Bridge #s 054201, 056501, and 019303 are being removed from this group and added to the newly created Bridge Group 45A. Those three bridges need to be accelerated. There is no budgetary change to this line item. Removed 019301 Removed 054201 Removed 056501
Pavement Capital Program | Shannock Road (Rt 112/Carolina Back Rd to Rt 2/South County Trail) | 9562 | Charlestown, Richmond | 3.474 | 0.35 | -3.124 | 2026 | 2027 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. This project may receive additional funding in the out years beyond the scope of the current STIP (2028 or later).
Traffic Safety Capital Program | Roadway Departure Mitigation - Guardrail and Median Improvements to Route 1 | 1469 | Charlestown, South Kingstown, Westerly | 3.6 | 4 | 0.4 | 2018 | 2018 | The cash flow for this line item is being revised to reflect the obligation of HSIP funds for this project in FFY18. The additional funding required to complete this project is now being obligated in FFY19.
Pavement Capital Program | US-1, Post Rd (Robin Hollow Rd to Prosser Tr) | 1423 | Charlestown, Westerly | 6 | 0.6 | -5.4 | 2023 | 2027 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Bridge Capital Program | Bridge Group 12A | 214 | Coventry | 7.7 | 7.7 | -1e-08 | 2018 | 2018 | The funding sources for this line item are being altered in this Amendment.
Bridge Capital Program | Bridge Group 42_H | 252 | Coventry | 1.85 | 6 | 4.15 | 2020 | 2021 | RIDOT has determined that this bridge group should be delayed 1 year to address readiness issues. The funding for this line item is being adjusted to suit the project's operational needs.
Bridge Capital Program | Bridge Group 58E | 199 | Coventry | 2.1 | 3.6 | 1.5 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Old Flat River Rd (Rt 117 to Rt 117) | 1311 | Coventry | 0.45 | 1.16 | 0.71 | 2024 | 2024 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Old Summit Rd & Susan Bowen Rd (Rt 117 to Rt 117) | 1309 | Coventry | 0.6 | 1.4 | 0.8 | 2020 | 2019 | This line item's schedule and budget are being altered to suit the project's operational needs.
Pavement Capital Program | Rt 117, Flat River Road (Hill Farm Rd to Read School House Road) | 9537 | Coventry | 1.105 | 0.34 | -0.765 | 2027 | 2027 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 3, Nooseneck Hill Road (Harkney Hill Rd to Reservoir Rd) | 9545 | Coventry | 1.36 | 0.37 | -0.99 | 2026 | 2027 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. Additional funding may be added to this project beyond the scope of the current STIP (2028 or later).
Transportation Alternatives | Sandy Bottom Road Streetscape | 5018 | Coventry | 1.25 | 1.25 | 0 | 2026 | 2027 | Project subject to delay due to lack of State Capital funds.
Transportation Alternatives | Trestle Trail - West Section - Paving | 9002 | Coventry | 5.5 | 0 | -5.5 | 2023 | N/A | Project deferred for cost and readiness review by Statewide Planning and RIDOT.
Bridge Capital Program | Bridge Group 51A | 187 | Coventry, Cranston, Warwick | 58.8535 | 60.18 | 1.3265 | 2018 | 2018 | The funding sources and cash flows are being streamlined in this amendment to reflect the scope of work being completed.
Bridge Capital Program | Bridge Group 69D | 114 | Coventry, Foster, Hopkinton, Richmond | 5.61 | 5.61 | 0 | 2018 | 2018 | The cash flow for this project is being adjusted to meet the needs of the project. Overall there is no budgetary change to this line item.
Pavement Capital Program | Rt. 116, North Road (Rt 12/Scituate Ave to Clarke Rd) | 9554 | Coventry, Scituate | 6.156 | 3.385 | -2.771 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Bridge Capital Program | Bridge Group 42B | 254 | Coventry, West Warwick | 5.85 | 5.85 | 0 | 2020 | 2020 | Adjusted cash flow to simplify sources.
Pavement Capital Program | Rt 3, Cowesett Ave and Tiogue Ave (Pilgrim Ave to Rt 2) | 1313 | Coventry, West Warwick | 3.2 | 5.78 | 2.58 | 2024 | 2025 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Bridge Capital Program | Bridge Group 32 | 31 | Cranston | 22.401 | 22.401 | 0 | 2019 | 2019 | Funding sources for this project are being adjusted. Overall, there is no budgetary change to this line item.
Bridge Capital Program | Bridge Group 34T | 185 | Cranston | 20.918 | 21.1 | 0.182 | 2018 | 2018 | This project is fully funded by the 2016 GARVEE issuance, which was shown in a prior STIP as a lump sum. The project funding that is now being shown reflects the actual cash flow needed to support the project as bid.
Bridge Capital Program | Bridge Group 51B | 188 | Cranston | 42.06 | 42.06 | 0 | 2020 | 2020 | Some funding is being advanced into the constrained period to support the acceleration of design and development work on this project. Overall, there is no budgetary change.
Bridge Capital Program | Bridge Group 59A | 58 | Cranston | 5.17 | 9.024 | 3.854 | 2018 | 2018 | The funding for this line item is being adjusted to meet the needs of the project, due to readiness and coordination with railroad.
Drainage Capital Program | Oaklawn Avenue/Wilbur Avenue Drainage Project | 5024 | Cranston | 2.25 | 2.25 | 0 | 2020 | 2020 | Minor changes to funding sources.
Pavement Capital Program | 1 R Improvements to Reservoir Avenue (Formerly: "Rt 2, Reservoir Ave (Sockanosset Cross Rd to Rt 12)") | 1314 | Cranston | 6.55 | 5.687 | -0.863 | 2018 | 2018 | The budget for this line item is being altered to meet the needs of the project. RIDOT has determined that this project can be completed with a reduction in funding.
Pavement Capital Program | Rt 1/Elmwood Ave (Providence T/L to Warwick T/L) | 9530 | Cranston | 0.79 | 0 | -0.79 | 2027 | N/A | This project is being deferred for future planning and study. For the time being, it will be delayed beyond the endpoint of this STIP (FFY2027).
Pavement Capital Program | Rt 12, Scituate Ave (Pippen Orchard Rd to Rt 51) | 1315 | Cranston | 3.8 | 7.78 | 3.98 | 2024 | 2024 | The budget for this line item is being altered ot meet the needs of the project.
Pavement Capital Program | Rt 2 Reservoir Ave (Park Ave to Rt 10) | 9544 | Cranston | 4.958 | 0 | -4.958 | 2026 | N/A | This project is being deferred for future planning and study. For the time being, it will be delayed beyond the endpoint of this STIP (FFY2027).
Pavement Capital Program | Rt 5, Atwood Ave (Cranston St to Rt 12/Phenix Ave) | 9550 | Cranston | 1.767 | 1.95 | 0.183 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt. 5, Atwood Avenue (Rt 12/Phenix Ave to Rt 14/Plainfield Pike) | 9560 | Cranston | 9.424 | 5.18 | -4.244 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt. 5/Oaklawn Avenue (Rt 2/New London Ave to Cranston St) | 9561 | Cranston | 15.782 | 7.88 | -7.902 | 2026 | 2025 | This line item's schedule and budget are being altered to suit the project's operational needs.
Pavement Capital Program | Warwick Ave (Park Ave to Broad Street) | 9564 | Cranston | 1.735 | 1.73 | -0.005 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Traffic Safety Capital Program | RISTARS - Localized Bottleneck Improvements to I-295 | 1531 | Cranston | 4.488 | 5.69 | 1.202 | 2021 | 2021 | $1.2M is being transferred into this line item in FFY22 from TIPID 1526 - Interchange Safety Improvements to Route 146/Route 116 Lincoln.
Transportation Alternatives | Safe Routes to School Infrastructure Improvements for Western Hills Middle School | 5021 | Cranston | 0.392 | 0.39 | -0.002 | 2018 | 2018 | Project Advanced by RIDOT to construction.
Bridge Capital Program | Immediate Action - Bridge | 1 | Cranston, Foster, Glocester, Hopkinton, North Kingstown, Pawtucket, Scituate, Statewide, Tiverton, Warwick | 74.657 | 69.323 | -5.334 | 2018 | 2018 | The funding sources included in this line item are being adjusted to include predominately state funding.
Bridge Capital Program | Bridge Group 09 | 11 | Cranston, Johnston | 4.267 | 4.267 | -1e-08 | 2018 | 2018 | The cash flow for this line item is being slightly altered to reflect the prior expenditures and anticipated needs of the project. There is no budgetary change to this line item.
Pavement Capital Program | I-295 (I-95 to Rt 5) | 1274 | Cranston, Johnston, Warwick, West Warwick | 18.5 | 1.86 | -16.64 | 2024 | 2026 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. RIDOT has determined that the budget included for this line item will support first year of work on project.
Pavement Capital Program | I-95 (Route 10 to I-195) | 9521 | Cranston, Providence | 1.281 | 0.66 | -0.621 | 2027 | 2027 | RIDOT has determined that the budget included for this line item will support the first year of work on the project.
Pavement Capital Program | Rt 10 (US-6 to Park Ave) | 1285 | Cranston, Providence | 7 | 7 | 0 | 2024 | 2024 | The cash flow for this project is being adjusted. Overall, there is no budgetary change to this line item.
Transportation Alternatives | Washington Secondary Bike Path Extension | 5215 | Cranston, Providence | 1.71 | 1.71 | 0 | 2022 | 2022 | Cash flow adjusted.
Pavement Capital Program | I-95 NB (160' south of Jefferson Blvd to 320' north of Laurens St overpass) | 9522 | Cranston, Warwick | 2.766 | 2.766 | 0 | 2026 | 2026 | The cash flow for this line item is being altered to meet the needs of the project. Overall, there is no budgetary change to this project.
Pavement Capital Program | I-95 SB (140' south of Service Ave to 90' North of Milford St overpass) | 9523 | Cranston, Warwick | 0.529 | 0.75 | 0.221 | 2027 | 2027 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 2, Bald Hill Rd and New London Ave (West Natick Ave to Rt 37) | 1411 | Cranston, Warwick | 4 | 4.76 | 0.76 | 2021 | 2025 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | Rt 5, Lambert Lind Hwy (Mayfield Ave to I-95) | 1415 | Cranston, Warwick | 6.5 | 6.5 | 0 | 2019 | 2019 | The cash flow for this line item is being altered to meet the needs of the project. Overall, there is no budgetary change to this line item.
Bridge Capital Program | Bridge Group 17C | 237 | Cumberland | 2.15 | 3.35 | 1.2 | 2020 | 2020 | The funding for this line item is being altered to meet the needs of the project.
Bridge Capital Program | Bridge Group 37T (I) | 81 | Cumberland | 10.69 | 10.7 | 0.01 | 2018 | 2018 | This project is fully funded by the 2016 GARVEE issuance, which was shown in a prior STIP as a lump sum. The project funding that is now being shown reflects the actual cash flow needed to support the project as bid.
Bridge Capital Program | Bridge Group 48A | 229 | Cumberland | 1.538 | 4.9 | 3.362 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project.
Bridge Capital Program | Bridge Group 62 | 59 | Cumberland | 14 | 14.1 | 0.1 | 2018 | 2018 | A very minor adjustment to the cash flow supporting this line item is being adjusted in this amendment.
Pavement Capital Program | Rt 114, Diamond Hill Rd (I-295 to Rt 120) | 1321 | Cumberland | 1.9 | 5.16 | 3.26 | 2023 | 2023 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 116, Angell Rd (Rt 122 to Rt 114) | 1322 | Cumberland | 2.1 | 3.86 | 1.76 | 2023 | 2023 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 122, Mendon Rd (I-295 to Ann & Hope Way) | 1318 | Cumberland | 5.1 | 5.4 | 0.3 | 2023 | 2023 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 122/Mendon Rd (Rt 120/Nate Whipple Highway to Homestead Rd) | 9539 | Cumberland | 2.993 | 3.1 | 0.107 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 123/Dexter St (Broad St to Massachusetts S/L) | 9540 | Cumberland | 3.693 | 3.9 | 0.207 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Sneech Pond Rd (Rt 120 to end) | 1319 | Cumberland | 0.5 | 0.5 | 0 | 2022 | 2022 | Project description was updated to clearly indicate which portion of Sneech Pond Rd. falls within the project limits. (Project limits changes from "Rt 120 to end" to "Rt 120 to the end of the eastern portion of Sneech Pond Rd")
Traffic Safety Capital Program | Intersection Safety Improvements to Route 114 between Bear Hill and I-295 Cumberland - Signal Upgrades | 1514 | Cumberland | 4.59 | 8.79 | 4.2 | 2018 | 2018 | Adjusted cash flow to match project expenditures.
Pavement Capital Program | I-295 (RT 146 to Massachusetts S/L) | 1276 | Cumberland, Lincoln | 0.9 | 0.58 | -0.32 | 2027 | 2027 | The budget for this line item is being altered to meet the needs of the project. RIDOT has determined that the budget included for this line item will support the first year of work on the project.
Traffic Safety Capital Program | Grade Crossing Surface and Signal Projects | 1443 | Cumberland, Lincoln, Newport, North Kingstown, Pawtucket, Providence, Woonsocket | 8.64 | 9.34 | 0.7 | 2018 | 2018 | RIDOT is recommending the removal of separate TIP IDs for each location and replacing the project limits for this item with "Statewide" to reflect the use of funding for this line item. (Project limits changes from "Locations for following RR TIP IDs: 2031, 2032, 5034, 5035, 5036, 5069, 5133, 5134, 5135, 5136, 5137, 5138, 5139, 5140, 5174, 5175, 5176, 5296, and 9010" to "Statewide")
Bridge Capital Program | Bridge Group 08 | 10 | Cumberland, Lincoln, Warwick, West Warwick | 24.476 | 24.784 | 0.308 | 2022 | 2022 | The funding for this line item is being altered to meet the needs of the project.
Bridge Capital Program | Bridge Group 17A | 235 | Cumberland, Smithfield | 24.54 | 24.54 | 0 | 2020 | 2019 | The specific funding sources being used to support this project are shifting. In addition, some funding is shifting into FFY19 to accelerate design work on this project. Overall, there is no budgetary change to this line item.
Pavement Capital Program | Rt 122, Mendon Rd and Cumberland Hill Rd (Eaton St to Hamlet Ave) | 1424 | Cumberland, Woonsocket | 3.4 | 3.22 | -0.18 | 2019 | 2024 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Bridge Capital Program | Bridge Group 58A | 195 | East Greenwich | 23.85 | 23.85 | 0 | 2018 | 2018 | The cash flow and funding sources for this line item are being adjusted. Overall, there is no budgetary change to this line item.
Pavement Capital Program | Rt. 2, South County Trail (Frenchtown Road to Route 4) | 9558 | East Greenwich | 5.496 | 3.02 | -2.476 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Bridge Capital Program | Bridge Group 05 | 7 | East Greenwich, Exeter, Warwick, West Greenwich | 9.819 | 10.4 | 0.581 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project.
Bridge Capital Program | Bridge Group 18A | 20 | East Greenwich, Narragansett, North Kingstown | 6.94 | 6.95 | 0.01 | 2020 | 2019 | The specific funding sources that are being used to support this project are being adjusted to meet its operational needs. The total budgetary change is minimal, but the funding streams supporting the project are being streamlined.
Bridge Capital Program | Bridge Group 18B | 218 | East Greenwich, North Kingstown | 4.3 | 3.35 | -0.95 | 2019 | 2019 | The funding for this line item is being altered to meet the needs of the project. RIDOT has determined that the project can be completed with a reduction in funding.
Pavement Capital Program | Rt 4 (Lafeyett Rd to Rt 403) | 1283 | East Greenwich, North Kingstown | 8 | 8.53 | 0.53 | 2024 | 2025 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | Rt 2, Quaker Lane (Division St. to Barton Corner Bridge Project Limit) | 9510 | East Greenwich, Warwick, West Warwick | 0.3 | 0.3 | 0 | 2018 | 2018 | Adding in a PTSID.
Bridge Capital Program | Bridge Group 49 | 48 | East Providence | 30 | 70 | 40 | 2025 | 2019 | The funding for this line item is being altered to meet the needs of the project. This project is being accelerated and funded with new federal appropriations secured in March 2019. The completion of this project will represent the largest single improvement to RIDOT's total bridge sufficiency rating.
Bridge Capital Program | Bridge Group 57D | 87 | East Providence | 1.8 | 1.8 | -1e-08 | 2018 | 2018 | The specific funding sources used to support this project are being altered. Overall, there is no budgetary change to this line item.
Bridge Capital Program | Bridge Group 57M | 89 | East Providence | 13.418 | 11.42 | -1.998 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project. RIDOT has determined that this project can be completed with a reduction in funding.
Bridge Capital Program | Bridge Group 57T (J) | 90 | East Providence | 7.5 | 7.5 | 0 | 2018 | 2018 | The funding sources to support this line item are being altered. Overall, there is no budgetary change to this line item.
Bridge Capital Program | Bridge Group 57TB | TBDWABR | East Providence | 0 | 40 | 40 | N/A | 2020 | This line item will support Phase II work on the Washington Bridge. The new structure number will be 070051. RIDOT will be submitting this project as a candidate for BUILD grant support, requesting an additional $25M in federal funding. This line item has been adjusted to show the estimated cost of the project WITHOUT that grant. If RIDOT receives BUILD support, the project will total $70M (including the grant and the required 20% match, an additional $5M. If RIDOT secures the grant, it will move forward with the $70M version of this project. If RIDOT does not receive the grant, this project will move forward with a budget of $40M. Added 070051
Bridge Capital Program | Bridge Group 69E | 202 | East Providence | 5.9 | 3.88 | -2.02 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project. RIDOT has determined that this project can be completed with a reduction in funding.
Pavement Capital Program | East Shore Exp (Rt 114 to US-6) | 1295 | East Providence | 2.7 | 3.3 | 0.6 | 2022 | 2023 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. The funding for this line item is being adjusted to meet the estimated needs of the project.
Pavement Capital Program | I-195 (Broadway to Massachusetts S/L) | 9518 | East Providence | 0.776 | 0.9 | 0.124 | 2027 | 2027 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | I-195 (Washington Bridge to Broadway) | 1272 | East Providence | 2 | 2 | 0 | 2021 | 2024 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | I-195/Taunton Avenue/Warren Ave. Interchange Improvements | 5042 | East Providence | 1.93 | 1.93 | 0 | 2018 | 2018 | Adding in project PTSID
Pavement Capital Program | Pawtucket Ave (Veteran's Memorial Parkway to Waterman Ave) | 9525 | East Providence | 9.7 | 5.34 | -4.36 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project. Additional funding may be aded in the outyears beyond the current scope of the STIP (2028 or later).
Pavement Capital Program | Rt 103, Bullocks Ave and Pawtucket Ave (Cresent View Ave to Veterans Mem. Ave) | 1326 | East Providence | 4.8 | 3.64 | -1.16 | 2023 | 2026 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. Additional funding may be added to this project in the years beyond the scope of the current STIP (2028 or later).
Pavement Capital Program | Rt 103, Veterans Memorial Prky (Warren Ave to South Broadway) | 1324 | East Providence | 1.7 | 3.12 | 1.42 | 2023 | 2025 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | Rt 103/Warren Ave (Pawtucket Ave to Broadway) | 9532 | East Providence | 4.907 | 4.907 | 0 | 2026 | 2025 | This line item's schedule is being altered to suit the project's operational needs. There is no budgetary change to this line item.
Pavement Capital Program | Rt 114, Pawtucket Ave (Taunton Ave to Warren Ave) | 1325 | East Providence | 1.3 | 5.51 | 4.21 | 2020 | 2025 | This project is being delayed due to readiness issues. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | Rt 114A/Pleasant St (Rt 114/Pawtucket Ave to Mass S/L) | 9533 | East Providence | 0.353 | 0.54 | 0.187 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 44 - Taunton Ave (Rt 1A/114 - Mass S/L) (Formerly: "US- 44, Taunton Ave (Rt 1A/114 to Mass.)") | 1323 | East Providence | 3 | 3 | 0 | 2018 | 2018 | Minor changes are being made to the cash flow for this line item. Overall, there is no budgetary change for this line item.
Pavement Capital Program | Rt 44, Taunton Ave (Pawtucket Ave to Hall St) | 9546 | East Providence | 1.429 | 1.6 | 0.171 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 6/Highland Ave (County St to MA S/L) | 9507 | East Providence | 1.69 | 1.69 | 0 | 2023 | 2023 | Minor changes to funding sources.
Transportation Alternatives | Safe Routes to School Infrastructure Improvements for Kent Heights Elementary School | 5039 | East Providence | 0.256 | 0.26 | 0.004 | 2018 | 2018 | Project Advanced by RIDOT to construction.
Transportation Alternatives | Safe Routes to School Infrastructure Improvements for Myron Francis Elementary School | 5040 | East Providence | 0.136 | 0.14 | 0.004 | 2018 | 2018 | Project Advanced by RIDOT to construction.
Transportation Alternatives | Ten Mile River Greenway, Segment 1-4 | 5045 | East Providence | 2.5 | 2.5 | 0 | 2025 | 2025 | The cash flow for this project is being adjusted. Overall, there is no budgetary change to this line item at this time. In addition, this project is being selected for review of purpose, need, readiness and cost estimate by Statewide Planning and RIDOT.
Pavement Capital Program | Rt 1A, Newport Ave (Federal St to Pawucket Ave) | 1375 | East Providence, Pawtucket | 2.8 | 6.16 | 3.36 | 2023 | 2024 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Bridge Capital Program | Bridge Group 77 | 68 | East Providence, Providence | 24.495 | 14.9 | -9.595 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project. RIDOT has determined that this project can be completed with a reduction in funding.
Bridge Capital Program | Bridge Group 38B | 212 | Exeter | 1 | 1 | 0 | 2018 | 2018 | Adding in a PTSID for this project.
Bridge Capital Program | Bridge Group 57J | 193 | Exeter | 2.04 | 2.04 | 0 | 2018 | 2018 | The project description is being updated in this amendment.
Bridge Capital Program | Bridge Group 67T | 96 | Exeter | 3.5 | 3.5 | 0 | 2018 | 2018 | The funding sources for this project are being adjusted to reflect the obligations associated with the project. There is no budgetary change to this line item.
Pavement Capital Program | Rt 2 - South County Trail (Rt 138 to Rt 102) | 1576 | Exeter, North Kingstown, South Kingstown | 7.6 | 7.6 | 0 | 2024 | 2025 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Bridge Capital Program | Bridge Group 16A | 18 | Foster, Glocester, Providence, Scituate, Smithfield | 9.248 | 10.67 | 1.422 | 2018 | 2018 | The funding for this line item is being adjusted to meet the needs of the project. In addition, the following 7 bridges are being removed and sent to Maintenance for vegitation removal: 009701,016601, 009201, 008501, 031601, 015701, and 015601. The remaining bridges require additional funding to be completed, which is being added to this line item. Removed 008501 Removed 009201 Removed 009701 Removed 015601 Removed 015701 Removed 016601 Removed 031601
Bridge Capital Program | Bridge Group 16B | 217 | Foster, Johnston, Providence, Scituate | 12.2 | 12.2 | 0 | 2018 | 2018 | Bridge #s 060901 and 060701 are being removed from this group and added into their own new group: 16D. While there are no budgetary changes to this group, the cash flow is being adjusted to accommodate the needs of the project. Removed 060701 Removed 060901
Pavement Capital Program | US-6 - Danielson Pike (Connecticut S/L to Rt 102) | 1579 | Foster, Scituate | 7 | 7 | 0 | 2022 | 2024 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | Rt 44/Putnam Pike (Rt 102/Chomist Hill Rd to Reservoir Rd) | 9547 | Glocester | 1.06 | 0.24 | -0.82 | 2026 | 2027 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. Additional funding may be added to this project in the out years beyond the scope of the current STIP (2028 or later).
Pavement Capital Program | Rt 44/Putnam Pke (Sprauge Hill Rd to Connecticut S/L) | 9549 | Glocester | 3.609 | 3.76 | 0.151 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 94, Reynolds Rd (Foster T/L to US-44) | 1329 | Glocester | 5.4 | 7.33 | 1.93 | 2022 | 2022 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | 1R Improvements to Route 44 - Contract 3B (RIDOT Maintance Facility to W. Greenville Rd.) (Formerly: "US-44, Putnam Pike (RIDOT Maintenance to West Greenville Rd)") | 1328 | Glocester, Smithfield | 8.68 | 9.735 | 1.055 | 2018 | 2018 | The budget for this line item is being altered to meet the needs of the project.
Bridge Capital Program | Bridge Group 07T (A) | 75 | Hopkinton | 3.93 | 15.805 | 11.875 | 2018 | 2018 | This project is fully funded by the 2016 GARVEE issuance, which was shown in a prior STIP as a lump sum. The project funding that is now being shown reflects the actual cash flow needed to support the project as bid.
Bridge Capital Program | Bridge Group 58D | 198 | Hopkinton | 0.5 | 3.2 | 2.7 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Clarks Falls Rd (Connecticut S/L to Main St) | 1332 | Hopkinton | 0.6 | 0.8 | 0.2 | 2020 | 2021 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Resurfacing Laurel and Maxson Streets (Formerly: "Resurfacing Laurel and Maxon Streets") | 1334 | Hopkinton | 1.5 | 1.95 | 0.45 | 2020 | 2022 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being adjusted to meet the estimated needs of the project.
Pavement Capital Program | Rt 3, Main St (Rt 216 to I-95) | 1331 | Hopkinton | 1.9 | 5.34 | 3.44 | 2022 | 2022 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Wellstown Rd (Rt 3 to Rt 216) | 1333 | Hopkinton | 0.7 | 0.96 | 0.26 | 2022 | 2022 | The budget for this line item is being altered to meet the needs of the project.
Transportation Alternatives | Main Street Handicap Access Sidewalk | 5058 | Hopkinton | 0.115 | 0.12 | 0.005 | 2026 | 2027 | Project subject to delay due to lack of State Capital funds.
Pavement Capital Program | I-95 (Connecticut S/L to Rt. 138) | 9520 | Hopkinton, Richmond | 6.223 | 0.57 | -5.653 | 2027 | 2027 | RIDOT has determined that the budget included for this line item will support the first year of work on this project.
Pavement Capital Program | Woodville Rd (Rt 3 to Switch Rd) | 1335 | Hopkinton, Richmond | 4 | 1.75 | -2.25 | 2018 | 2018 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Narragansett Ave (End to Southwest Ave) | 1336 | Jamestown | 1.4 | 1.4 | 0 | 2022 | 2022 | Minor changes are being made to the cash flows in this line item.
Transportation Alternatives | Jamestown Bridge Bike/Pedestrian Access | 5060 | Jamestown | 0.8 | 0.8 | 0 | 2022 | 2022 | The cash flow for this project is being adjusted. Overall, there is no budgetary change to this line item at this time. In addition, this project is being selected for review of purpose, need, readiness and cost estimate by Statewide Planning and RIDOT.
Bridge Capital Program | Bridge Group 09T | 184 | Johnston | 33.53 | 41.13 | 7.6 | 2018 | 2018 | This project is fully funded by the 2016 GARVEE issuance, which was shown in a prior STIP as a lump sum. The project funding that is now being shown reflects the actual cash flow needed to support the project as bid.
Bridge Capital Program | Bridge Group 35T | 186 | Johnston | 3.159 | 15.24 | 12.081 | 2018 | 2018 | This project is fully funded by the 2016 GARVEE issuance, which was shown in a prior STIP as a lump sum. The project funding that is now being shown reflects the actual cash flow needed to support the project as bid.
Pavement Capital Program | Greenville Ave (Providence C/L to Salina Ave) | 9516 | Johnston | 0.784 | 0.38 | -0.404 | 2027 | 2027 | The budget for this line item is being altered to meet the needs of the project. RIDOT has determined that this project can be completed with a reduction in funding.
Pavement Capital Program | Greenville Ave (Salina Ave to Rt 5/Atwood Ave) | 9517 | Johnston | 1.747 | 1.95 | 0.203 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project. Additional funding may be made available for this project in the Outyears beyond the scope of the current STIP (2028 or later).
Pavement Capital Program | Rt 5, Atwood Ave (Central Ave to Rt 14) | 1337 | Johnston | 1.45 | 3.08 | 1.63 | 2022 | 2022 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 6A (Hartford Ave, C-2) (Formerly: "Reconstruction of Hartford Avenue") | 1339 | Johnston | 9.8 | 3.34 | -6.46 | 2018 | 2018 | This line item will serve as Phase 2 of construction on Rt 6A, consisting of pavement milling and an initial overlay. The final phase of this project will be shown in a new line item titled: "Rt 6A (Hartford Ave, C-3)."
Pavement Capital Program | Rt 6A (Hartford Ave, C-3) | TBDPAVE2 | Johnston | 0 | 8.6 | 8.6 | N/A | 2022 | This line item completes the work begun in TIPID #1339
Pavement Capital Program | I-295 (Rt 5 to Rt 146) | 1275 | Johnston, Lincoln, Smithfield | 16 | 2.14 | -13.86 | 2024 | 2026 | RIDOT has determined that this pavement segment can withstand an additonal 2 year(s) of delay. RIDOT has determined that the budget included for this line item will support the first year of work on the project.
Pavement Capital Program | Rt 44/Putnam Pike (Rt 104/Waterman Ave to I-295 ) | 9548 | Johnston, North Providence, Smithfield | 5.943 | 3.26 | -2.683 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Bridge Capital Program | Bridge Group 16D | TBD16D | Johnston, Providence | 0 | 17 | 17 | N/A | 2022 | New Bridge Group. Adding bridges # 060901 and 060701 from BG-16B. RIDOT has estimated that these two bridges will require the funding shown beginning in the outyears. Added 060901 Added 060701
Pavement Capital Program | Rt 128/Killingly Street (Hartford Ave to Greenville Ave) | 9542 | Johnston, Providence | 4.597 | 4.7 | 0.103 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | US-6 (I-295 to Rt 10) | 1280 | Johnston, Providence | 10.5 | 0.53 | -9.97 | 2024 | 2027 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | US Route 6 Hartford Ave (Formerly: "US-6, Hartford Pike and Hartford Ave (Danielson Pk to I-295)") | 1393 | Johnston, Scituate | 1.3 | 9.04 | 7.74 | 2018 | 2018 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Winsor Ave (Rt 116 to Greenville Ave) | 1338 | Johnston, Scituate | 1.7 | 1.35 | -0.35 | 2019 | 2018 | Altering funding to reflect project needs. Project achieved substantial completion in July 2018. Also changing the project name to match the RhodeWorks Quarterly Report.
Traffic Safety Capital Program | Intersection Safety Improvements to Route 6 – Scituate/Johnston | 1509 | Johnston, Scituate | 4.2 | 4.2 | 0 | 2019 | 2019 | Minor changes are being made to the cash flow for this line item. Overall, there is no budgetary change for this line item.
Pavement Capital Program | Rt 5, Greenville Ave and Sanderson Rd (Atwood Ave to US-44) | 1341 | Johnston, Smithfield | 2.1 | 4.59 | 2.49 | 2024 | 2024 | The budget for this line item is being altered to meet the needs of the project.
Bridge Capital Program | *REMOVED* Bridge Group 36 (Formerly: "Bridge Group 36") | 35 | Lincoln | 0.562 | 0 | -0.562 | 2027 | N/A | This bridge (#074901) is part of Immediate needs Steel Repairs Contract 3. The bridge group is being removed as the needs of the bridge are already being serviced.
Bridge Capital Program | Bridge Group 62T (K) | 93 | Lincoln | 14.89 | 14.15 | -0.74 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project. RIDOT has determined that this project can be completed with a reduction in funding.
Pavement Capital Program | Albion Rd (Old River Rd to Eagle Rock Rd) | 1349 | Lincoln | 0.4 | 0.94 | 0.54 | 2022 | 2022 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | New River Rd (School St to Mussey Brook Rd) | 1342 | Lincoln | 0.7 | 3.29 | 2.59 | 2022 | 2026 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the project funding is being adjusted to meet the estimated needs of ther project.
Pavement Capital Program | Railroad St (Manville Hill Rd to Rt 126) | 1343 | Lincoln | 3.2 | 2.77 | -0.43 | 2018 | 2018 | This project has been completed. Its cash flow is being updated accordingly.
Pavement Capital Program | Rt 116/George Washingtown Highway (Lincoln Mall to Albion Rd) | 9534 | Lincoln | 1.784 | 1.98 | 0.196 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 123, Great Rd and Front St (Great Rd to Old River Rd) | 1346 | Lincoln | 1.1 | 2.21 | 1.11 | 2022 | 2022 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 126, Smithfield Ave (Pawtucket C/L to Woodland St) | 1348 | Lincoln | 1.5 | 3.34 | 1.84 | 2021 | 2022 | RIDOT has determined that this pavement can withstand an additional 1 year(s) of delay.
Pavement Capital Program | Rt 126/River Road (Curtis Ln to Rt 116/George Washington Highway) | 9508 | Lincoln | 8.07 | 8.07 | 0 | 2022 | 2024 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability.
Pavement Capital Program | School St (Rt 126 to Main St) | 1347 | Lincoln | 3 | 3 | 0 | 2021 | 2022 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability.
Traffic Safety Capital Program | *REMOVED* Interchange Safety Improvements to Route 146/Route 116 Lincoln - Acceleration/Deceleration Lanes (Formerly: "Interchange Safety Improvements to Route 146/Route 116 Lincoln - Acceleration/Deceleration Lanes") | 1528 | Lincoln | 4 | 0 | -4 | 2021 | N/A | The work included in this line item is being consolidated into Bridge Group 62T (K). As a result, this line item may be eliminated.
Bridge Capital Program | Bridge Group 39 | 38 | Lincoln, North Providence | 14.682 | 21.25 | 6.568 | 2020 | 2018 | The funding for this line item is being altered to meet the needs of the project. While some funding was expended on this project in FFY18, work will continue in FFY21.
Pavement Capital Program | Rt 146 (I-95 to 0.6 miles south of Sherman Ave) | 1291 | Lincoln, North Providence, Providence | 4.5 | 0 | -4.5 | 2018 | N/A | This project reached substantial completion in FFY18. The funding shown in FY18 was not needed to complete the project, and it is being removed to reflect actual expenditures.
Traffic Safety Capital Program | Route 146 Guide Sign and Sign Structure Replacement | 1512 | Lincoln, North Providence, Providence | 6.5 | 5.29 | -1.21 | 2019 | 2019 | Minor changes are being made to the cash flows for this line item. RIDOT has determined that this project can be completed with a reduction in funding.
Pavement Capital Program | Rt 146, Eddie Dowling Hwy (I-295 to Rt 146A) | 1292 | Lincoln, North Smithfield | 4.9 | 4.9 | 0 | 2022 | 2024 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability.
Pavement Capital Program | Sayles Hill Rd (Rt 146 to Rt 126) | 1371 | Lincoln, North Smithfield | 1.4 | 2.97 | 1.57 | 2022 | 2022 | The budget for this line item is being altered to meet the needs of the project.
Traffic Safety Capital Program | Intersection Safety Improvements to Route 146 Corridor North Smithfield - Signal Improvements | 1459 | Lincoln, North Smithfield | 4 | 4 | 0 | 2019 | 2023 | This project is being delayed to the outyears due to a lack of currently available funding. There may be an opportunity to revisit and revise the scope of this project in the future when new funding becomes available.
Bridge Capital Program | Bridge Group 13B | 216 | Lincoln, Providence | 6.323 | 6.3484 | 0.0254 | 2018 | 2018 | The specific funding sources that are being used to support this project are being adjusted to meet its operational needs. The total budgetary change is minimal, but the funding streams supporting the project are being streamlined.
Bridge Capital Program | Bridge Group 17D | 238 | Lincoln, Smithfield | 3.42 | 5.42 | 2 | 2020 | 2020 | The funding for this line item is being altered to meet the needs of the project and address regulatory issues associated with the project.
Bridge Capital Program | Bridge Group 35 | 34 | Lincoln, Smithfield | 23.717 | 23.717 | 0 | 2020 | 2019 | The funding for this line item is being accelerated due to readiness.
Pavement Capital Program | Rt 123, Jenckes Hill Rd (Albion to Rt 246) | 1350 | Lincoln, Smithfield | 2.1 | 4.5 | 2.4 | 2024 | 2024 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Twin River Road (Rt 7/Douglas Pike to Lincoln Woods State Park entrance) | 9563 | Lincoln, Smithfield | 1.845 | 0.25 | -1.595 | 2026 | 2027 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. This project may receive additional funding in the out years beyond the scope of the current STIP (2028 or later).
Pavement Capital Program | East Main Rd (Peckham Rd to Simmons Rd) | 1351 | Little Compton | 1.8 | 2.64 | 0.84 | 2023 | 2023 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Meeting House Ln (Rt 77 to South of Commons Rd) | 1352 | Little Compton | 2.5 | 2.5 | 0 | 2020 | 2025 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability.
Pavement Capital Program | Snell Rd (East Main Rd to Long Hwy) | 1353 | Little Compton | 0.9 | 1.106 | 0.206 | 2018 | 2018 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | South Commons Rd and Simmons Rd (Brownell Rd to East Main Rd) | 1354 | Little Compton | 1.3 | 2.99 | 1.69 | 2019 | 2023 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being adjusted to meet the estimated needs of ther project.
Pavement Capital Program | 1 R Improvements to Green Lane (Formerly: "Greene Ln (Navy Base to Rt 114)") | 1358 | Middletown | 2 | 2.8 | 0.8 | 2019 | 2019 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 138, East Main Rd (Porstmouth T/L to Aquidneck Ave) | 1357 | Middletown | 1.6 | 4.33 | 2.73 | 2024 | 2024 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 138A, Aquidneck Ave (East Main Rd to Green End Ave) | 1355 | Middletown | 5.28 | 6.2 | 0.92 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 214, Valley Rd (Green End Ave to Rt 138) | 1359 | Middletown | 1.7 | 2.7 | 1 | 2024 | 2024 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt. 138A, Aquidneck Ave. (Valley Rd. to Purgatory Rd.) | 5070 | Middletown | 0.9 | 0.9 | 0 | 2020 | 2021 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability.
Pavement Capital Program | Two Mile Corner | 1356 | Middletown | 3.4 | 3.9 | 0.5 | 2018 | 2018 | The budget for this line item is being altered to meet the needs of the project.
Traffic Safety Capital Program | Intersection Safety Improvements to lower Aquidneck Avenue | 1467 | Middletown | 3.2 | 2.2 | -1 | 2018 | 2018 | Minor changes are being made to the cash flow for this line item. RIDOT has determined that this project can be completed with a reduction in funding.
Transportation Alternatives | Purgatory Road Sidewalk Installation | 5072 | Middletown | 0.64 | 0.64 | 0 | 2021 | 2021 | Project cash flow adjusted to suit operational needs.
Bridge Capital Program | Bridge Group 15B | 210 | Middletown, Narragansett, New Shoreham, Newport, Portsmouth, Tiverton | 8.51 | 8.1 | -0.41 | 2018 | 2018 | Bridge # 064921 is being added from this line item and funding is being adjusted to meet the operational needs of the project. RIDOT has determined that this reduction in funding will still allow the project to be completed. Added 064921
Pavement Capital Program | Pell Bridge Ramps - Phase 1 (Formerly: "JT Connell Hwy (Admiral Kalbfus to Rt 114)") | 1364 | Middletown, Newport | 2.4 | 13.1 | 10.7 | 2020 | 2018 | This line item's schedule and budget are being altered to suit the project's operational needs.
Pavement Capital Program | Rt 114, West Main Rd (John Kesson to Mill Ln) | 1360 | Middletown, Portsmouth | 6.5 | 6.63 | 0.13 | 2022 | 2022 | The budget for this line item is being altered to meet the needs of the project.
Transportation Alternatives | East Main Road Shared Use Path - Hedly St to Enterprise Drive | 9005 | Middletown, Portsmouth | 3 | 3 | 0 | 2021 | 2020 | Project advanced due to readiness.
Pavement Capital Program | Rt 1A, Boston Neck Rd (Bridgetown Rd to Sprague Bridge) | 1362 | Narragansett | 4.4 | 9.91 | 5.51 | 2022 | 2025 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | South Pier Rd (Rt 108 to Boon St) | 1361 | Narragansett | 1.65 | 1.87 | 0.22 | 2020 | 2026 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project. Additional funding may be added to this project in the Outyears beyond the scope of the current STIP (2028 or later).
Transportation Alternatives | Ocean Road Beautification - Phase 1 & 2 | 5093 | Narragansett | 0.45 | 0.45 | 0 | 2026 | 2026 | Project cash flow maintained.
Transportation Alternatives | Safe Routes to School Infrastructure Improvements for Narragansett Pier Middle School | 5088 | Narragansett | 0.64 | 0.64 | 0 | 2018 | 2019 | Subject to minor re-sequencing due to environmental permitting requirements.
Transportation Alternatives | William C. O'Neill Bike Path Extension - Phase 4B | 5089 | Narragansett | 8.43 | 3 | -5.43 | 2018 | 2019 | Project delayed due to local readiness issues. The funding for this line item is being reduced to support a less costly alternative version of this project.
Pavement Capital Program | Bridgetown Rd (US-1 to Rt 1A) | 1401 | Narragansett, South Kingstown | 1.5 | 2.7 | 1.2 | 2019 | 2026 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | Chapel Street - Sidewalks | 5098 | New Shoreham | 0.712 | 0.85 | 0.138 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Transportation Alternatives | Corn Neck Road - Sidewalks | 5097 | New Shoreham | 1.145 | 1.15 | 0.005 | 2026 | 2027 | Project subject to delay due to lack of State Capital funds.
Transportation Alternatives | West Side Road - Sidewalks | 5096 | New Shoreham | 1.22 | 1.22 | 0 | 2018 | 2019 | Project delayed due to local readiness issues.
Pavement Capital Program | Reconstructing Pell Bridge Approaches | 9201 | Newport | 38.7 | 53.6 | 14.9 | 2018 | 2018 | The funding for this line item is being adjusted to suit the operational needs of the project and to include the usage of BUILD Grant proceeds secured in early 2019.
Traffic Safety Capital Program | HSIP Statewide Crosswalk Enhancements (Formerly: "Pedestrian Improvements to Memorial Boulevard – Newport") | 1441 | Newport | 2.35 | 2.35 | 0 | 2019 | 2019 | Updating the project description and name to reflect the usage of this line item. Minor changes are being made to the cash flow for this line item. Overall, there is no budgetary change for this line item.
Transportation Alternatives | Bellevue Avenue ADA Sidewalk/Access Improvements | 5107 | Newport | 1.13 | 3.03 | 1.9 | 2023 | 2022 | Project advanced due to readiness. Project budget increase resulting from transfer of funding from TIP ID 5108 (Marlborough Street West Marlborough Streetscape Improvements) at request of the City.
Transportation Alternatives | Farewell Street Pavement Preservation and Sidewalk Improvements | 5106 | Newport | 1.2 | 1.2 | 0 | 2026 | 2025 | Project advanced to allow for design and permitting in 2025.
Transportation Alternatives | Marlborough Street/West Marlborough Streetscape Improvements | 5108 | Newport | 1.9 | 0 | -1.9 | 2021 | N/A | The City completed this project using City funds and has requested transfer of existing budget to TIP ID 5107 (Bellevue Avenue ADA Sidewalk Access Improvements).
Transportation Alternatives | Newport North End Bicycle/Pedestrian Connectivity and Safety Improvements | 9003 | Newport | 7.2 | 0 | -7.2 | 2019 | N/A | The work in this line item overlaps with the Pell Bridge Ramps project. This line item is being eliminated, and its funding is transitioning to support Phase 2 of the Pell Bridge Ramps project, TIPID 9201.
Transportation Alternatives | Thames and Spring Streetscape Improvements | 5105 | Newport | 8.5 | 8.5 | 0 | 2021 | 2020 | Advanced due to project readiness.
Bridge Capital Program | Bridge Group 46A | 222 | North Kingstown | 5.211 | 8.528 | 3.317 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project.
Drainage Capital Program | Essex Road and Post Road Intersection - Drainage | 5128 | North Kingstown | 1.5 | 6.5 | 5 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project. Concerns outside the highway right of way require mitigation, including drainage, historic, and environmental issues.
Pavement Capital Program | Rt 102, Phillips St (Rt 1A to US-1) | 1367 | North Kingstown | 1 | 1.44 | 0.44 | 2024 | 2024 | The budget for this line item is being alterecd to meet the needs of the project.
Pavement Capital Program | Rt 1A, Boston Neck Rd (Brown St to Rt 138) | 1365 | North Kingstown | 4.6 | 7.02 | 2.42 | 2023 | 2025 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | Rt 1A, West Main St (US-1 to Brown St) | 1368 | North Kingstown | 1.6 | 1.6 | 0 | 2019 | 2022 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability.
Pavement Capital Program | Rt. 1, Tower Hill Road Road (West Main Street to Rt 4/Rt 1) | 9553 | North Kingstown | 9.028 | 4.96 | -4.068 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Transit Operations - RIDOT | Wickford Junction Operations | 7103 | North Kingstown | 3 | 0 | -3 | 2018 | N/A | Funding for this line item has been consolidated into TIP ID 7105.
Transportation Alternatives | Belleville House to Wickford village sidewalk and crosswalk improvements | 5125 | North Kingstown | 0.353 | 0.35 | -0.003 | 2026 | 2027 | Project subject to delay due to lack of State Capital funds.
Transportation Alternatives | Post Road - Curbing and Sidewalks | 5120 | North Kingstown | 2 | 2 | 0 | 2019 | 2022 | Based on meeting with Town, RIDOT has re-sequenced project to coincide with other projects.
Transportation Alternatives | Sidewalks on Route 102 (Home Depot - Wickford Junction) | 5127 | North Kingstown | 0.44 | 0.44 | 0 | 2026 | 2027 | Project subject to delay due to lack of State Capital funds
Transit Operations - RIDOT | T-Link Bus/Rail Connections | 7108 | North Kingstown, Providence, Warwick | 5 | 5 | 0 | 2018 | 2018 | Minor changes are being made to the cash flows for this line item. Overall, there is no budgetary change for this line item.
Pavement Capital Program | Improvements to Tower Hill Rd (Government Center to Rt. 4) (Formerly: "US-1, Tower Hill Rd (Government Center to Rt 4)") | 1279 | North Kingstown, South Kingstown | 10 | 10 | 0 | 2020 | 2022 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability.
Bridge Capital Program | Bridge Group 24A | TBD24A | North Providence | 0 | 2 | 2 | N/A | 2019 | New Bridge Group. The replacement of Bridge #014501 is being accelerated, so it is being moved to this newly created bridge group from Bridge Group 24. The funding for this line item is being adjusted to meet the needs of the project. Added 014501
Pavement Capital Program | Rt 104, Farnum Pk and Waterman Ave (Rt 116 to Rt 15) | 1394 | North Providence, Smithfield | 4.7 | 7.78 | 3.08 | 2024 | 2024 | The budget for this line item is being altered to meet the needs of the project.
Bridge Capital Program | Bridge Group 13C | 232 | North Smithfield | 3.45 | 3.45 | 0 | 2020 | 2020 | The specific funding sources that are being used to support this project are being adjusted to meet its operational needs. There is no budgetary change, but the funding streams supporting the project are being streamlined.
Bridge Capital Program | Bridge Group 38A | 211 | North Smithfield | 6.748 | 6.2 | -0.548 | 2018 | 2019 | RIDOT has determined that this bridge group should be delayed 1 year to address readiness issues. RIDOT has determined that this project can be completed with a reduction in funding.
Bridge Capital Program | Bridge Group 38T (L) | 82 | North Smithfield | 8.44 | 13.7 | 5.26 | 2018 | 2018 | The funding fo this line item is being altered to meet the needs of the project.
Bridge Capital Program | Bridge Group 53 | 52 | North Smithfield | 4.588 | 3.8 | -0.788 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project. RIDOT has determined that this project can be completed with a reduction in funding.
Bridge Capital Program | Bridge Group 70C | 99 | North Smithfield | 6.3 | 6.3 | 0 | 2018 | 2018 | The funding sources supporting this project have been adjusted. Overall, there is no budgetary change to this line item.
Pavement Capital Program | Rt 102/Bronco Highway (Main St to Rt 5/Providence Pike) | 9531 | North Smithfield | 4.672 | 0.47 | -4.202 | 2026 | 2027 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. This project may receive additional funding in the out years beyond the current scope of the STIP (2028 or later).
Pavement Capital Program | Rt 146 (Rt 146A to Massachusetts S/L) | 1293 | North Smithfield | 8.52 | 8.52 | 0 | 2023 | 2023 | Minor changes to funding sources.
Pavement Capital Program | Rt 5, Greenville Rd (Rt 5 to Rt 146) | 1370 | North Smithfield | 2.1 | 0.24 | -1.86 | 2024 | 2027 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. Additional funding may be added to this project in the out years beyond the scope of the current STIP (2028 or later).
Pavement Capital Program | School St (Green St to Rt 146) | 1369 | North Smithfield | 1.6 | 3.27 | 1.67 | 2024 | 2025 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Bridge Capital Program | Bridge Group 13A | 215 | North Smithfield, Providence | 6.71 | 6.71 | 0 | 2018 | 2018 | The PTSID for this line item is being altered.
Pavement Capital Program | Rt 146A (Park Ave to Rt 104) | 1372 | North Smithfield, Woonsocket | 1.35 | 0.18 | -1.17 | 2023 | 2027 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Bridge Capital Program | Bridge Group 03 | 5 | Pawtucket | 14 | 14 | 0 | 2019 | 2019 | The funding source type supporting this line item is being adjusted in FFY19 in this amendment.
Bridge Capital Program | Bridge Group 03T (F) | 72 | Pawtucket | 12.35 | 15.86 | 3.51 | 2018 | 2018 | This project is fully funded by the 2016 GARVEE issuance, which was shown in a prior STIP as a lump sum. The project funding that is now being shown reflects the actual cash flow needed to support the project as bid.
Bridge Capital Program | Bridge Group 31 | 30 | Pawtucket | 9.95 | 8.7 | -1.25 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project. RIDOT has determind that this project can be completed with a reduction in funding.
Bridge Capital Program | Bridge Group 56D | 105 | Pawtucket | 12.98 | 7.75 | -5.23 | 2018 | 2018 | The project description for this line item is being altered along with schedule due to readiness and coordination with the railroad.
Pavement Capital Program | Central Ave (George Bennett Highway to Mass S/L) | 9513 | Pawtucket | 0.948 | 0 | -0.948 | 2027 | N/A | This project is being deferred for future planning and study. For the time being, it will be delayed beyond the endpoint of this STIP (FFY2027).
Pavement Capital Program | I-95 (Exchange St to Garden St) | 9505 | Pawtucket | 2.36 | 2.36 | 0 | 2024 | 2024 | Minor changes are being made to the cash flows for this line item. Overall, there is no budgetary change to this line item.
Pavement Capital Program | I-95 Resurfacing, C-2 (Pawtucket) (Formerly: "I-95 (Rt 15 to Mass.)") | 1271 | Pawtucket | 3.7 | 2.91 | -0.79 | 2018 | 2018 | The budget for this line item is being altered to meet the needs of the project. RIDOT has determined that this project can be completed with a reduction in funding.
Pavement Capital Program | Pavement Preservation to Rt 1A (Newport Ave) (Formerly: "Rt 1A, Newport Ave (Federal St to Massachusetts S/L)") | 1373 | Pawtucket | 3.2 | 5 | 1.8 | 2018 | 2018 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 126/Smithfield Ave (Rt 15/Mineral Spring Ave to Lincoln T/L) | 9541 | Pawtucket | 1.258 | 1.54 | 0.282 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Transit Capital Program - RIDOT | Pawtucket Town Landing Rehabilitation | TBDPLR | Pawtucket | 0 | 0.8 | 0.8 | N/A | 2020 | RIDOT has estimated that this project will cost approximately $800k to complete. The project will be supported by some OtherFederal funds and the required 20% state match. (Project limits changes from "" to "West Bank of the Seekonk River, Pawtucket Town Landing, South of Division St at Taft St.")
Transit Capital Program - RIDOT | Pawtucket/Central Falls Transit Center | 5011 | Pawtucket | 40.8025 | 50.9104 | 10.1079 | 2019 | 2019 | Adjusted cash flow and sources to reflect the most recently available project information.
Transportation Alternatives | Blackstone River Bikeway - Segment 3A-1 | 9012 | Pawtucket | 1.6 | 0 | -1.6 | 2019 | N/A | Project shifted to Green Economy Bond funding provided by DEM for implementation
Transportation Alternatives | Blackstone River Bikeway - Segment 3A-2 | 9013 | Pawtucket | 7 | 7 | 0 | 2023 | 2023 | Cash flow altered slightly. No overall budgetary change.
Transportation Alternatives | Slater Mill Phase II | 5155 | Pawtucket | 0.75 | 0.75 | 0 | 2018 | 2019 | Project delayed due to local readiness issues.
Transportation Alternatives | Ten Mile Mile River Greenway | 5157 | Pawtucket | 0.5 | 0 | -0.5 | 2024 | N/A | Project scope calls for parking lot and canoe/kayak launch. RIDOT recommending evaluation by City and DEM for funding under DEM program offerings.
Pavement Capital Program | I-95 Resurfacing Program, Contract 2B (Providence and Pawtucket) (Formerly: "I-95 (Barbara Leonard Way to Mulberry St)") | 1270 | Pawtucket, Providence | 8.3 | 8.3 | 0 | 2021 | 2022 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability.
Pavement Capital Program | US-1, Pawtucket Ave and North Main St (Garden St to Rochambeau Ave) | 1386 | Pawtucket, Providence | 2.7 | 8.78 | 6.08 | 2022 | 2024 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Traffic Safety Capital Program | Roadway Departure Mitigation - Systemic High Friction Surface Treatments | 1498 | Pawtucket, Providence | 1.1 | 1.1 | 0 | 2018 | 2018 | Changing project location. (Project limits changes from "I-95 at Pawtucket S-Curves and I-95 at Thurbers Avenue curve" to "Route 37 at Natick and Reynolds Road") (Project limits changes from "I-95 at Pawtucket S-Curves and I-95 at Thurbers Avenue curve" to "Route 37 at Natick and Reynolds Road")
Pavement Capital Program | East Main Road 1R Improvements (Formerly: "Rt 138, East Main Rd & Park Ave (East Main - Turnpike Ave to Boyds Ln and Park Ave - Rt 138 to Norseman Drive)") | 1378 | Portsmouth | 3 | 7 | 4 | 2018 | 2018 | The funding for this line item is being altered to meet the operational needs of the project.
Pavement Capital Program | Route 24 Improvements (Formerly: "Rt 24 (Rt 114 to Hummocks Ave)") | 1286 | Portsmouth | 6.9 | 7.75 | 0.85 | 2018 | 2018 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 114, West Main Rd (Rt 24 to Turnpike Ave) | 1376 | Portsmouth | 2.74 | 2.74 | 0 | 2023 | 2023 | Minor changes to funding sources.
Pavement Capital Program | Rt 138, East Main Rd (Hedly St to Middletown T/L) | 1380 | Portsmouth | 3.9 | 8.78 | 4.88 | 2021 | 2022 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | Rt 138, East Main Rd (Turnpike Ave to Hedley Ave) | 1379 | Portsmouth | 15 | 14.98 | -0.02 | 2019 | 2024 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | Sprague St (East Main Rd to Bristol Ferry Rd/Turnpike Ave) | 1377 | Portsmouth | 1 | 2.08 | 1.08 | 2023 | 2023 | The budget for this line item is being adjusted to reflect the needs of the project. In addition, $780k is being added to this line item from TIP ID 5166 - Sprague Street Sidewalks, at the request of the Town of Portsmouth.
Traffic Safety Capital Program | Aquidneck Ave Improvements | 2026 | Portsmouth | 0 | 0.565 | 0.565 | N/A | 2018 | Project now fully funded with proposed cash flow.
Transportation Alternatives | Aquidneck Island Bikeway - Melville Connector | 5161 | Portsmouth | 2.16 | 2.16 | 0 | 2024 | 2024 | Project PTSID altered; PTSID still to be determined.
Transportation Alternatives | East Main Road Sidewalks | 5164 | Portsmouth | 2 | 0 | -2 | 2021 | N/A | Project Advanced to construction and is complete.
Transportation Alternatives | Mount Hope Bay Bicycle Improvements | 5162 | Portsmouth | 0.16 | 0.16 | 0 | 2023 | 2023 | Project PTSID altered; PTSID still to be determined.
Transportation Alternatives | Sprague Street Sidewalks | 5166 | Portsmouth | 0.78 | 0 | -0.78 | 2018 | N/A | In a letter to RIDOT, the Town of Portsmouth has requested that the funding allocated to this line item be grouped into TIP ID 1377, a repavement project on Sprague Street set to begin in FFY23. That change is reflected in the pavement capital program project adjustments.
Transportation Alternatives | Stone Bridge Rehabilitation Study - Island Park | 5171 | Portsmouth | 0.08 | 0 | -0.08 | 2022 | N/A | Study no longer necessary. Project complete.
6/10 Project | 6/10 Project | 125 | Providence | 390 | 0 | -390 | 2018 | N/A | This line item is being moved to the bridge capital program. The cash flow for this project is also being adjusted to suit the latest estimates of the project's financial needs.
Bridge Capital Program | 6/10 Project | 125 | Providence | 0 | 343.27 | 343.27 | N/A | 2018 | This line item is being moved to the bridge capital program. The cash flow for this project is also being adjusted to suit the latest estimates of the project's financial needs.
Bridge Capital Program | Bridge Group 01 | 3 | Providence | 11.542 | 10.714 | -0.828 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project. While this project initially had heavier cash flows in FFY19 and FFY20, the needs of the project have shifted to FFY21. RIDOT has determined that the project can be completed with a net reduction in funding.
Bridge Capital Program | Bridge Group 02 | 4 | Providence | 19.789 | 18.134 | -1.655 | 2020 | 2020 | Bridge #065601 has been removed from this Bridge Group. In addition, the cash flow for this line item is being altered to meet the needs of the project. RIDOT has determined that this project can be completed with a reduction in funding. Removed 065601
Bridge Capital Program | Bridge Group 02T (D) | 71 | Providence | 7.61 | 10.3 | 2.69 | 2018 | 2018 | This project is fully funded by the 2016 GARVEE issuance, which was shown in a prior STIP as a lump sum. The project funding that is now being shown reflects the actual cash flow needed to support the project as bid.
Bridge Capital Program | Bridge Group 06 | 8 | Providence | 12.005 | 10.5 | -1.505 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project based on RIDOT's estimates of the funding required to complete it.
Bridge Capital Program | Bridge Group 13D | 233 | Providence | 12.56 | 12.56 | -1e-08 | 2020 | 2020 | The specific funding sources that are being used to support this project are being adjusted to meet its operational needs. There is no budgetary change, but the funding streams supporting the project are being streamlined.
Bridge Capital Program | Bridge Group 16T (M) | 78 | Providence | 1.6 | 10.07 | 8.47 | 2018 | 2018 | This project is fully funded by the 2016 GARVEE issuance, which was shown in a prior STIP as a lump sum. The project funding that is now being shown reflects the actual cash flow needed to support the project as bid.
Bridge Capital Program | Bridge Group 20A | 213 | Providence | 20.1 | 17 | -3.1 | 2018 | 2018 | The funding sources for this line item are being altered in this Amendment due to readiness and coordination with the railroad as well.
Bridge Capital Program | Bridge Group 21A | 244 | Providence | 6.2 | 12.5 | 6.3 | 2020 | 2022 | RIDOT has determined that this bridge group should be delayed 2 years to address readiness issues and coordination with railroad. The funding for this line item is being adjusted to suit the project's operational needs.
Bridge Capital Program | Bridge Group 21B | 245 | Providence | 3.4 | 6.4 | 3 | 2021 | 2022 | RIDOT has determined that this bridge group should be delayed 1 year to address readiness issues and cooridnation with railroad. The funding for this line item is being adjusted to suit the project's operational needs.
Bridge Capital Program | Bridge Group 21D | 247 | Providence | 4.5 | 2.5 | -2 | 2024 | 2024 | Smith St RR Bridge (#092801) and Orms St RR Bridge (#092901) are being removed from this bridge group, and funding is being reduced to service the remaining needs of the project, due to readiness and coordination with railroad. Bridge 092801 is moving to Bridge Group 21E, which Bridge 092901 is being moved to Bridge Group 21F. Removed 092801 Removed 092901
Bridge Capital Program | Bridge Group 21E | TBD21E | Providence | 0 | 1.2 | 1.2 | N/A | 2020 | This bridge (092801) is being moved to its own group. The schedule for completion of this bridge is being accelerated to comply with safety needs and procedures, due to readiness and coordination with railroads. Added 092801
Bridge Capital Program | Bridge Group 21F | TBD21F | Providence | 0 | 1.8 | 1.8 | N/A | 2020 | This bridge (092901) is being moved to its own group. The schedule for completion of this bridge is being accelerated to comply with safety needs and procedures, due to readiness and coordination with railroads. Added 092901
Bridge Capital Program | Bridge Group 30 | 29 | Providence | 18.103 | 13.8 | -4.303 | 2018 | 2018 | Bridge #065701 is being removed to create Bridge Group 30B. Work on the remaining bridge #065901 will be delayed accordingly. While some funds were expended to support this project in FFY18, work will continue in FFY21. RIDOT has determined that this project can be completed with a reduction in funding. Removed 065701
Bridge Capital Program | Bridge Group 30B | TBD30B | Providence | 0 | 23.63 | 23.63 | N/A | 2021 | New Bridge Group created with bridges 065701 and 065601 from Bridge Groups 30 and 02 respectively. Design work on these bridges will begin in FFY21 and require the proposed funding shown. Added 065701 Added 065601
Bridge Capital Program | Bridge Group 38C | 226 | Providence | 3.474 | 3.42 | -0.054 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project. RIDOT has determined that this project can be completed with a minor reduction in funding.
Bridge Capital Program | Bridge Group 40 | 39 | Providence | 5 | 2.4 | -2.6 | 2023 | 2023 | Bridge #087401, which is already under construction with 100% state funds, in being removed from this group. As a result, the total cost of the remaining bridges in this group will be reduced. Funding is being removed from this line item to reflect that change. Removed 087401
Bridge Capital Program | Bridge Group 40B | 228 | Providence | 3.5 | 3.51 | 0.01 | 2018 | 2018 | The funding sources supporting this line item are being altered, and a very minor budgetary change is being made to support the needs of this project.
Bridge Capital Program | Bridge Group 57E | 192 | Providence | 1 | 1.917 | 0.917 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project, due to readiness and coordination with railroad.
Bridge Capital Program | Bridge Group 59C | 92 | Providence | 8.2 | 13.9 | 5.7 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project.
Bridge Capital Program | Bridge Group 75 | 67 | Providence | 10.4 | 6.032 | -4.368 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project. RIDOT has determined that this project can be completed with a reduction in funding.
Bridge Capital Program | Bridge Group 75T 5B (I) | 208 | Providence | 120 | 245.91 | 125.91 | 2018 | 2018 | The cash flow for this line item has been adjusted to include the addition of 2019 GARVEE funds to support the replacement of the Providence I-95 Northbound Viaduct. $200M in GARVEE funding will now support this project, repaid by a portion of the federal funds previously allocated to this line item.
Maintenance Capital Program | Materials Facility Renovation | 7908 | Providence | 2.5 | 3.33 | 0.83 | 2018 | 2018 | The funding for this line item is being altered to meet operational needs.
Pavement Capital Program | Dudley St Connector (Eddy St to Allens Ave) | 1425 | Providence | 2.7 | 0 | -2.7 | 2023 | N/A | This project is being deferred for future planning and study. For the time being, it will be delayed beyond the endpoint of this STIP (FFY2027).
Pavement Capital Program | I-195 (I-95 to East Providence T/L) | 9519 | Providence | 1.617 | 0.31 | -1.307 | 2026 | 2027 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. The budget included for this line item will support first year of work on project.
Pavement Capital Program | I-195 Relocation, Gano St, Contract 18 (Formerly: "Gano St (India St to Trenton)") | 1381 | Providence | 3.23 | 0.65 | -2.58 | 2018 | 2018 | This line item was supported by revenues from I-195 land sales. It is fully funded and under construction.
Pavement Capital Program | North Main Street Providence (Mill St. to Colonial Rd.) | 9524 | Providence | 0.891 | 0 | -0.891 | 2027 | N/A | This project is being deferred for future planning and study. For the time being, it will be delayed beyond the endpoint of this STIP (FFY2027). (Project limits changes from "North Main Street Providence (Mill St. to Colonial Rd.)" to "")
Pavement Capital Program | Randall Street (Charles St. to North Main St.) | 9526 | Providence | 0.12 | 0 | -0.12 | 2027 | N/A | This project is being deferred for future planning and study. For the time being, it will be delayed beyond the endpoint of this STIP (FFY2027).
Pavement Capital Program | Rt 1/Elmwood Ave (Cranston T/L to Roger Williams Ave) | 9529 | Providence | 5.575 | 0.56 | -5.015 | 2026 | 2027 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. This project may receive additional funding in the years beyond the scope of the current STIP (2028 or later).
Pavement Capital Program | Rt 6A/Hartford Ave (Rt 14/Plainfield St to Killingly Street) | 9552 | Providence | 5.62 | 3.09 | -2.53 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | US-44, Smith St (Lyndhurst Ave to I-95) | 1384 | Providence | 0.1 | 1.1 | 1 | 2018 | 2018 | Adjusting FFY18 funding to reflect project expenditures.
Pavement Capital Program | US-6 (Rt 10 to I-95) | 1281 | Providence | 2.4 | 0.34 | -2.06 | 2023 | 2027 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Traffic Safety Capital Program | Arterial Traffic Signal Improvements - Allens Avenue | 1510 | Providence | 3.197 | 3.197 | 0 | 2019 | 2019 | The project description for this line item is being updated.
Traffic Safety Capital Program | Pedestrian and Bicycle Safety Improvements - Exchange Street | 1461 | Providence | 1.62 | 0.9 | -0.72 | 2018 | 2018 | Minor changes are being made to the funding sources that support this line item. The funding shown reflects the expenditure for this line item in FFY18.
Transportation Alternatives | Cathedral Square Enhancement Project | 5182 | Providence | 0.48 | 0.48 | 0 | 2023 | 2026 | Project delayed for cost and readiness review by Statewide Planning and RIDOT
Transportation Alternatives | CityWalk Providence Pedestrian and Bicycle Enhancement Project | 5183 | Providence | 0.94 | 1.38 | 0.44 | 2018 | 2020 | Project delayed due to local readiness issues. Project budget increased to match balance remaining per Sub-Recipient Agreement.
Transportation Alternatives | Downtown Providence Pedestrian Wayfinding Project | 5200 | Providence | 0.05 | 0 | -0.05 | 2025 | N/A | RIDOT is recommending that signage be included in other on-going City and State projects. The amount of staff time required to insure that federal requirements are met may potentially approach the total cost of the project.
Transportation Alternatives | Kennedy Plaza | 1460 | Providence | 2.7 | 2.7 | 0 | 2018 | 2019 | Including three earmarks for Kennedy plaza, which total $182K. Project delayed due to local readiness issues.
Transportation Alternatives | NBT/WRG: Providence Woonasquatucket Greenway Enhancements | 5178 | Providence | 5.51 | 4.98 | -0.53 | 2018 | 2019 | Project being assessed for partial inclusion in the Providence Viaduct (NB) Replacement, Bridge Group 75TB (I).
Transportation Alternatives | Providence Bicycle Infrastructure Enhancements | 5199 | Providence | 1.8 | 1.8 | 0 | 2023 | 2023 | The cash flow is being adjusted for this line item. In addition, this project is being selected for review of purpose, need, readiness and cost estimate by Statewide Planning and RIDOT.
Transportation Alternatives | Providence Bicycle Master Plan | 1488 | Providence | 0.1 | 0 | -0.1 | 2019 | N/A | Plan withdrawn by City of Providence.
Transportation Alternatives | Providence Waterplace and Riverwalk Repairs and Walkway Improvements | 5202 | Providence | 4.05 | 4.05 | 0 | 2022 | 2026 | Project delayed for cost and readiness review by Statewide Planning and RIDOT. Potential sea-level rise and other environmental considerations may further complicate this project.
Transportation Alternatives | SanSouci/Woony (Green Economy Bond) | 5131 | Providence | 0.55 | 0 | -0.55 | 2018 | N/A | Project shifted to Green Economy Bond funding provided by DEM for implementation
Bridge Capital Program | Bridge Group 05TB (B2) | 73 | Richmond | 1.93 | 8.93 | 7 | 2018 | 2018 | This project is fully funded by the 2016 GARVEE issuance, which was shown in a prior STIP as a lump sum. The project funding that is now being shown reflects the actual cash flow needed to support the project as bid.
Bridge Capital Program | Bridge Group 54A | 189 | Richmond | 19 | 20.9 | 1.9 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project.
Bridge Capital Program | Bridge Group 57F | 88 | Richmond | 7.3 | 8.55 | 1.25 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Old Switch Rd (Mechanic St to Switch Rd) | 1387 | Richmond | 1.2 | 1.7 | 0.5 | 2025 | 2025 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt. 2, South County Trail (Charlestown T/L to South Kingstown T/L) | 9557 | Richmond | 1.916 | 0.26 | -1.656 | 2026 | 2027 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Traffic Safety Capital Program | Roundabout at Intersection of Rt. 138 and Rt. 112 | 5219 | Richmond | 2.1 | 3.5 | 1.4 | 2018 | 2018 | The cash flow and funding supporting this line item are being adjusted to meet the needs of the project.
Bridge Capital Program | Bridge Group 45A | TBD45A | Richmond, South Kingstown, Westerly | 0 | 4.5 | 4.5 | N/A | 2019 | New bridge group. This bridge group will consist of bridge #s 054201, 056501, 019303. Added 054201 Added 056501 Added 019303
Bridge Capital Program | Bridge Group 16C | 234 | Scituate | 3.6948 | 3.7 | 0.0052 | 2020 | 2020 | Cash flow simplified.
Pavement Capital Program | 1 R Improvements to Rockland Road (Formerly: "Rockland Rd (Central Pk to Danielson Pk)") | 1388 | Scituate | 2.52 | 2.52 | 0 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Central Pk & Battey Meeetinghouse Rd | 1389 | Scituate | 5.2 | 5.5 | 0.3 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Danielson Pk (Rt 102 to West Greenville Rd) | 1392 | Scituate | 4.8 | 4.8 | 0 | 2024 | 2019 | RIDOT has accelerated this project to improve pavement conditions in the area.
Pavement Capital Program | Rt 115, Main St (Rt 116 to Jackson Flat Rd) | 1391 | Scituate | 2 | 2.6 | 0.6 | 2019 | 2019 | The funding for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 6 - (Rt 102 - Rt 101) (Formerly: "US-6, Scituate Bypass and Hartford Pike (Rt 102 to Danielson Pk)") | 1390 | Scituate | 2.7 | 7.85 | 5.15 | 2019 | 2018 | This line item's schedule and budget are being altered to meet the needs of the project.
Bridge Capital Program | Bridge Group 10 | 12 | Smithfield | 12 | 12.1 | 0.1 | 2019 | 2019 | A minor adjustment is being made to the funding to support this line item.
Pavement Capital Program | Rt 116/Smith Ave (Orchard Ave to Rt 44/Putnam Pike) | 9535 | Smithfield | 1.704 | 1.87 | 0.166 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | US-44, Putnam Pike (Commerce St. to I-295) | 5227 | Smithfield | 1.4 | 3 | 1.6 | 2020 | 2023 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Traffic Safety Capital Program | Intersection Safety Improvements to Route 44/Smithfield Commons Smithfield - Dual Left Turn Lanes | 1476 | Smithfield | 1.3 | 1.4 | 0.1 | 2018 | 2018 | The funding for this line item is being adjusted to meet the needs of the project. This includes a minor cash flow change in FFY19.
Transportation Alternatives | Old County Road Sidewalk Installation Project | 5229 | Smithfield | 0.71 | 0.71 | 0 | 2026 | 2027 | Project subject to delay due to lack of State Capital funds.
Transportation Alternatives | Safe Routes to School Infrastructure Improvements for Gallagher Middle and McCabe Elementary Schools | 5224 | Smithfield | 0.216 | 0.21 | -0.006 | 2018 | 2018 | Project advanced by RIDOT to construction.
Bridge Capital Program | Bridge Group 54B | 190 | South Kingstown | 9 | 11.46 | 2.46 | 2018 | 2020 | RIDOT has determined that this bridge group should be delayed 2 years to address readiness issues. The funding for this line item is being adjusted to suit the project's operational needs, due to coordination with railroad.
Pavement Capital Program | Flagg Rd (Plains Rd to Old North Rd) | 1398 | South Kingstown | 0.9 | 1.5 | 0.6 | 2020 | 2022 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Old Tower Hill Rd (Rt 108 to US-1) | 1395 | South Kingstown | 1.5 | 3.95 | 2.45 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Post Rd (US-1 to US-1) - Camp Fuller area | 1400 | South Kingstown | 1.4 | 3.22 | 1.82 | 2023 | 2023 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 108/Kingstown Road (Rt. 138/Mooresfield Rd to Saugatucket Rd/Curtis Corner Rd) | 9509 | South Kingstown | 0.3 | 0.3 | 0 | 2018 | 2018 | Adding in a PTSID.
Pavement Capital Program | Rt 138, Kingstown Rd Contract-1 (Railroad Ave to Rt 108) | 1399 | South Kingstown | 9 | 10.42 | 1.42 | 2019 | 2023 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | Rt 138, Kingstown Rd Contract-2 (Route 2 to Fairgrounds) | 1397 | South Kingstown | 7 | 7 | 0 | 2020 | 2023 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | US-1, Commodore Perry Hwy (550 ft east of Charlestown T/L to Succotash Rd) | 1277 | South Kingstown | 4.2 | 1.48 | -2.72 | 2018 | 2018 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Upper College Road Complete Streets Reconstruction | 5324 | South Kingstown | 0.4 | 0 | -0.4 | 2018 | N/A | This line item is being removed from the FFY2018-FFY2027 STIP.
Transportation Alternatives | URI/South County Bike Path Connector and Extension | 5245 | South Kingstown | 2.6 | 0 | -2.6 | 2018 | N/A | Project shifted to Green Economy Bond funding provided by DEM for implementation
Maintenance Capital Program | Train Station Maintenance and Repairs - RICAP | 7901 | South Kingstown, Westerly, Woonsocket | 4.2 | 4.55 | 0.35 | 2018 | 2018 | The funding for this line item is being altered to meet operational needs.
Bridge Capital Program | Bridge Inspection | 7201 | Statewide | 0 | 82 | 82 | N/A | 2018 | Shifting this line item from the Bridge Maintenance Program to the Bridge Capital Program.
Bridge Capital Program | Expansion Joint Cleaning/Spot Painting | 7202 | Statewide | 0 | 6.13 | 6.13 | N/A | 2018 | Shifting this line item from the Bridge Maintenance Program to the Bridge Capital Program. A portion of the actions funded by this line item will now be supported by the Maintenance Operations line item in the STIP.
Bridge Capital Program | Projects Currently Under Construction | 2 | Statewide | 68.342 | 0 | -68.342 | 2018 | N/A | Utilizing the funding for this line item to support other projects in need of additional support throughout the bridge capital program.
Bridge Capital Program | Rhodeworks Toll Facilities | TBDRTF | Statewide | 0 | 61.58 | 61.58 | N/A | 2018 | This line item was included in a previous STIP. It is being included in this STIP amendment to show the latest cash flow supporting the project.
Bridge Maintenance | Bridge Inspection | 7201 | Statewide | 82 | 0 | -82 | 2018 | N/A | Shifting this line item from the Bridge Maintenance Program to the Bridge Capital Program.
Bridge Maintenance | Bridge Permits | 7203 | Statewide | 1 | 0 | -1 | 2018 | N/A | The actions funded by this line item will now be supported by the Maintenance Operations line item in the STIP.
Bridge Maintenance | Expansion Joint Cleaning/Spot Painting | 7202 | Statewide | 84.732 | 0 | -84.732 | 2018 | N/A | Shifting this line item from the Bridge Maintenance Program to the Bridge Capital Program. A portion of the actions funded by this line item will now be supported by the Maintenance Operations line item in the STIP.
Contingency - Inflation | Contingency - Inflation | 1427 | Statewide | 25.309 | 9.4 | -15.909 | 2020 | 2027 | This line item is being reduced because its funds are being allocated to programs in need of support. In future years, as project costs are refined and cash flows are updated, this line item may be replenished with excess funding through a STIP adjustment or amendment.
Debt Service | Garvee Debt Service | 7702 | Statewide | 496.246 | 615.079 | 118.833 | 2018 | 2018 | The funding for this line item is increasing to accommodate debt service payments required to support a $200M GARVEE bond issuance. The annual debt service costs will total approximately $16M per year, beginning with a smaller payment due in FFY20.
Debt Service | Motor Fuel Bond Debt Service - GARVEE Match | 7703 | Statewide | 64.175 | 70.775 | 6.6 | 2018 | 2018 | The funding for this line item is being altered to meet operational needs.
Drainage Capital Program | Immediate Needs | 2033 | Statewide | 1.55 | 1.91 | 0.36 | 2018 | 2018 | The funding for this line item is being altered to meet operational needs.
Headquarters Operations | Contract Administration-3860106 | TBDCA | Statewide | 0 | 4.5 | 4.5 | N/A | 2019 | This office establishes formal business arrangements between theDepartment and suppliers of all major goods and services that the Department deems necessary to purchase from the private sector.
Headquarters Operations | DOA Bureau of Audit Centralization Costs | TBDBA | Statewide | 0 | 7.2 | 7.2 | N/A | 2019 | As part of the State’s centralization efforts, RIDOT pays for auditing staff housed in the Department of Administration to assist RIDOT in ensuring that the auditing process is coordinated and efficient.
Headquarters Operations | DOA DBE Staff Member | 7611 | Statewide | 0.9 | 0.54 | -0.36 | 2018 | 2018 | The funding for this line item is being altered to meet operational needs.
Headquarters Operations | DOA Purchasing Centralization Costs | 7610 | Statewide | 4.4 | 5.48 | 1.08 | 2018 | 2018 | The funding for this line item is being altered to meet operational needs.
Headquarters Operations | Design (Legacy Consultant with Staff) Bridge | 7613 | Statewide | 16.5607 | 0 | -16.5607 | 2018 | N/A | This line item is no longer needed and is being removed from the STIP.
Headquarters Operations | Design (Legacy Consultant with Staff) Traffic | 7614 | Statewide | 3.6937 | 0 | -3.6937 | 2018 | N/A | This line item is no longer needed and is being removed from the STIP.
Headquarters Operations | Director's Office/Press Office-3850101 & 3860101 (Formerly: "Director's Office - 3850101 & 3860101") | 7601 | Statewide | 19.5 | 26.45 | 6.95 | 2018 | 2018 | Altering the funding for this line item to suit operational needs.
Headquarters Operations | Division of Project Management Operational Costs-3870121 | TBDPMO | Statewide | 0 | 28.8 | 28.8 | N/A | 2019 | This office is is responsible for overseeing all phases of a project from start to finish including design, environmental, construction, and materials testing
Headquarters Operations | External Audit - 3860103 & 3850104 | 7607 | Statewide | 4.6 | 0.46 | -4.14 | 2018 | 2018 | External Audit no longer resides at DOT. It has moved under the DOA Bureau of Audits. The funding for this line item is being transferred to a new line item (DOA Bureau of Audit Centralization Costs, TIPID to be determined) to reflect organizational changes and efficiencies.
Headquarters Operations | Health & Safety Programs - 3870118 | 7612 | Statewide | 4 | 9.184 | 5.184 | 2018 | 2018 | The funding for this line item is being altered to meet operational needs.
Headquarters Operations | Human Resources-3850103 (includes centralization costs) (Formerly: "Human Resources - 3850103") | 7604 | Statewide | 16 | 14.2 | -1.8 | 2018 | 2018 | Updating the project description and name to reflect the usage of this line item and altering the funding for this line item to suit operational needs.
Headquarters Operations | ICR/Overhead Recoveries | 7615 | Statewide | -90 | -144 | -54 | N/A | N/A | The funding for this line item is being altered to meet operational needs.
Headquarters Operations | Legal - 3850102 | 7603 | Statewide | 10 | 24.85 | 14.85 | 2018 | 2018 | The funding for this line item is being altered to meet operational needs.
Headquarters Operations | Legislative Office-3850111 | TBDLO | Statewide | 0 | 4.032 | 4.032 | N/A | 2019 | This office coordinates with elected officials throughout the state on matters of RIDOT policy, projects, initiatives, and special events.
Headquarters Operations | Office of Highway Safety - 3850106 | 7606 | Statewide | 7.3 | 7.03 | -0.27 | 2018 | 2018 | The funding for this line item is being altered to meet operational needs.
Headquarters Operations | Office of Stormwater Operational Costs-3870119 | TBDSWO | Statewide | 0 | 14.4 | 14.4 | N/A | 2019 | This office is is responsible for the scope, plan, design, and maintenance of stormwater systems. The section ensures that new construction projects that the Department undertakes use innovative ways toprevent contamination of both surface and groundwater, before discharging into Rhodes Island’s vitalwaterways.
Headquarters Operations | Office of Transit Operational Costs-3870120 | TBDOT | Statewide | 0 | 7.425 | 7.425 | N/A | 2019 | This office develops, plans, and implements projects the provide convenient transitions between transportation modes, including ferry and rail services.
Headquarters Operations | Operational Contingency | TBDOC | Statewide | 0 | 45 | 45 | N/A | 2019 | This line item supports operational needs of the Department that arise throughout each year.
Headquarters Operations | Press Office - 3850101 | 7602 | Statewide | 11.25 | 0.75 | -10.5 | 2018 | 2018 | This line item is being combined with TIP ID 7601 in FFY19 onward to match the operating budget.
Headquarters Operations | Property Management - 3850105 | 7605 | Statewide | 62.7 | 17.7 | -45 | 2018 | 2018 | The funding for this line item is being altered to meet operational needs.
Headquarters Operations | Technology - 3860106 | 7609 | Statewide | 73.506 | 72.006 | -1.5 | 2018 | 2018 | The funding for this line item is being altered to meet operational needs.
Maintenance Capital Program | Maintenance - Capital Equipment Replacement - Total | 7902 | Statewide | 56.95 | 52.95 | -4 | 2018 | 2018 | The funding for this line item is being altered to meet operational needs.
Maintenance Capital Program | Maintenance Facility Asset Protection | 7906 | Statewide | 5.55 | 5.96 | 0.41 | 2018 | 2018 | The funding for this line item is being altered to meet operational needs.
Maintenance Capital Program | Salt Storage Facilities | 7903 | Statewide | 10 | 11.4 | 1.4 | 2018 | 2018 | The funding for this line item is being altered to meet operational needs.
Maintenance Operations | Immediate Action | 7507 | Statewide | 5 | 0.5 | -4.5 | 2018 | 2018 | This line item is being reduced and its funds are being consolidated into TIP ID 7503 - Maintenance Operations.
Maintenance Operations | Maintenance Operations (Formerly: "Maintenance") | 7503 | Statewide | 257.8944 | 345.415 | 87.5206 | 2018 | 2018 | OutYear funding from TIPID 7202 - Expansion Joint Cleaning/Spot Painting, is being moved into this line item.
Maintenance Operations | Pothole Repair Contract (Formerly: "Pothole Repair") | 7504 | Statewide | 6 | 6 | 0 | 2018 | 2018 | Updating the project description and name.
Maintenance Operations | TMC Equipment Asset Management | TBDTMC | Statewide | 0 | 2.25 | 2.25 | N/A | 2019 | This line item supports the regular maintainance, repair, and replacement of equipment utilized by the Traffic Management Center (TMC). This funding may be used to replace the most obselete TMC equipment--including video equipment, changeable message signs, servers and network equipment, highway advisory radios, and Uninterruptable Power Supply Systems (UPS)--on an asset management basis.
Maintenance Operations | Vehicle Purchases & Maintenance (includes fuel) (Formerly: "Vehicle Maintenance (includes fuel)") | 7502 | Statewide | 59.7018 | 66.149 | 6.4472 | 2018 | 2018 | Updating the project description and name to reflect the usage of this line item and altering the funding for this line item to suit operational needs.
Maintenance Operations | Winter Operations (Formerly: "Winter Maintenance") | 7501 | Statewide | 130 | 189.35 | 59.35 | 2018 | 2018 | Updating the project description and name to reflect the usage of this line item and altering the funding for this line item to suit operational needs.
Pass Throughs | RIPTA CMAQ | 7110 | Statewide | 30.16 | 31.19 | 1.03 | 2018 | 2018 | This line item is being altered to reflect the latest proposed changes to RIPTA's expenditure of CMAQ pass through by RIDOT.
Pavement Capital Program | 2026 Pavement Capital Program Immediate Needs Set-Aside (5% of $120M for construction/0.75% for design) | 9511 | Statewide | 6 | 3.3 | -2.7 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project. RIDOT has determined that this project can be completed with a reduction in funding.
Pavement Capital Program | 2027 Pavement Capital Program Immediate Needs Set-Aside (5% of $120M for construction/0.75% for design) | 9512 | Statewide | 6.9 | 3.8 | -3.1 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project. RIDOT has determined that this project can be completed with a reduction in funding.
Pavement Capital Program | Chip Seal, Surface Seal | 7305 | Statewide | 0 | 42.88 | 42.88 | N/A | 2018 | This line item is being moved into the Pavement Capital Program from the Pavement Maintenance Program to reflect the linkage between pavement maintenance and preservation work with larger reconstruction and reclamation projects.
Pavement Capital Program | Crack Sealing | 7301 | Statewide | 0 | 23 | 23 | N/A | 2018 | This line item is being moved into the Pavement Capital Program from the Pavement Maintenance Program to reflect the linkage between pavement maintenance and preservation work with larger reconstruction and reclamation projects.
Pavement Capital Program | Design Set-Aside for Remainder of FY 2028 Program | 9515 | Statewide | 10 | 0 | -10 | 2027 | N/A | This line item is being reduced to service the needs of programmed projects.
Pavement Capital Program | Immediate Action | 7302 | Statewide | 0 | 2.5 | 2.5 | N/A | 2018 | This line item is moving to the Pavement Capital Program from the Pavement Maintenance program. The funding is being preserved.
Pavement Capital Program | Pavement Program Planning | 1265 | Statewide | 34.5 | 0 | -34.5 | 2019 | N/A | This line item is being reduced to service the needs of the projects programmed throughout the Pavement Capital Program.
Pavement Capital Program | Pavement Projects Currently Under Construction | 1264 | Statewide | 55.6 | 14 | -41.6 | 2019 | 2025 | The line item is being reduced to service the needs of programmed projects, particularly in the constrained period.
Pavement Capital Program | Permits | 7304 | Statewide | 0 | 10 | 10 | N/A | 2018 | This line item is being moved into the Pavement Capital Program from the Pavement Maintenance Program to reflect the linkage between pavement maintenance and preservation work with larger reconstruction and reclamation projects.
Pavement Maintenance | Chip Seal, Surface Seal | 7305 | Statewide | 38.88 | 0 | -38.88 | 2018 | N/A | This line item is being moved into the Pavement Capital Program from the Pavement Maintenance Program to reflect the linkage between pavement maintenance and preservation work with larger reconstruction and reclamation projects.
Pavement Maintenance | Crack Sealing | 7301 | Statewide | 20 | 0 | -20 | 2018 | N/A | This line item is being moved into the Pavement Capital Program from the Pavement Maintenance Program to reflect the linkage between pavement maintenance and preservation work with larger reconstruction and reclamation projects.
Pavement Maintenance | Immediate Action | 7302 | Statewide | 2.5 | 0 | -2.5 | 2018 | N/A | This line item is being moved into the Pavement Capital Program from the Pavement Maintenance Program to reflect the linkage between pavement maintenance and preservation work with larger reconstruction and reclamation projects.
Pavement Maintenance | Inspection | 7303 | Statewide | 2.5 | 0 | -2.5 | 2018 | N/A | This line has been included in the Maintenance Operations line item of the STIP.
Pavement Maintenance | Permits | 7304 | Statewide | 10 | 0 | -10 | 2018 | N/A | This line item is being moved into the Pavement Capital Program from the Pavement Maintenance Program to reflect the linkage between pavement maintenance and preservation work with larger reconstruction and reclamation projects.
Planning - Program Development | Asset Management - Data Collection - Mapping GIS (Formerly: "ASSET MANAGEMENT - DATA COLLECTION - MAPPING") | 7808 | Statewide | 33.8954 | 33.8934 | -0.002 | 2018 | 2018 | Minor changes are being made to the cash flows for this line item. Overall, a minor budgetary change is being made to this line item.
Planning - Program Development | Capital Program Planning-3870101 | 7801 | Statewide | 28.762 | 20.879 | -7.883 | 2018 | 2018 | RIDOT has determined that this project can be completed with a reduction in funding.
Planning - Program Development | Construction Oversight - 3870105 | 7803 | Statewide | 21 | 21 | 0 | 2018 | 2018 | Minor changes are being made to the cash flow for this line item. Overall, there is no budgetary change for this line item.
Planning - Program Development | Design Oversight - 3870104 | 7802 | Statewide | 22 | 10.3 | -11.7 | 2018 | 2018 | RIDOT has determined that this project can be completed with a reduction in funding.
Planning - Program Development | Materials Section - 3870117 | 7804 | Statewide | 24 | 13.6 | -10.4 | 2018 | 2018 | RIDOT has determined that this project can be completed with a reduction in funding.
Planning - Program Development | Motor Fuel Tax Evasion Program | 5119 | Statewide | 1.595 | 1.595 | 0 | 2018 | 2018 | Minor changes are being made to the cash flow for this line item. Overall, there is no budgetary change for this line item.
Planning - Program Development | Narragansett Indians | 7806 | Statewide | 6 | 0.6 | -5.4 | 2018 | 2018 | Payments under this line item are being phased out. The new MOU governing the use of funding previously housed in this line item is project-based. Therefore, RIDOT will include funds to offset the cost of coordination with the tribe within the funding for relevant projects as needed.
Planning - Program Development | Office of Civil Rights - 3850110 | TBDOCR | Statewide | 0 | 12.6 | 12.6 | N/A | 2019 | This office is responsible for supporting contractors, consultants, and sub-recipients toachieve full compliance with the federal and state civil rights laws and equal employment requirements.
Planning - Program Development | Program Planning | 7811 | Statewide | 16.605 | 1.76 | -14.845 | 2018 | 2018 | The funding for this line item is now being included in the Planning Division line item of the TIP
Planning - Program Development | RI DEPARTMENT OF ENVIRONMENTAL MANAGEMENT | 7807 | Statewide | 1.2 | 1.2 | 0 | 2018 | 2018 | The funding sources supporting this line item are being altered. Overall, there is no budgetary change to this line item.
Planning - Program Development | RI SHPO | 7805 | Statewide | 1.2 | 1.47 | 0.27 | 2018 | 2018 | Changing the funding for this line item to meet operational needs.
Traffic Maintenance | Immediate Action - RISTARS | 1118 | Statewide | 10 | 10 | 0 | 2018 | 2018 | Minor changes are being made to the cash flows for this line item. Overall, there is no budgetary change for this line item.
Traffic Maintenance | Permits | 1117 | Statewide | 1.5 | 0 | -1.5 | 2018 | N/A | The actions funded by this line item will now be supported by the Maintenance Operations line item in the STIP.
Traffic Safety Capital Program | 2019 Interchange Safety Improvements | 9611 | Statewide | 2.91 | 2.91 | 0 | 2018 | 2018 | Altering the PTSID.
Traffic Safety Capital Program | Exit Renumbering - Limited Access Facilities | 1435 | Statewide | 2.824 | 3.502 | 0.678 | 2018 | 2018 | Budget updated to meet the operational needs of this line item.
Traffic Safety Capital Program | Guardrail Improvements | 1433 | Statewide | 13.35 | 12.5 | -0.85 | 2019 | 2021 | RIDOT has determined that this project can be completed with a reduction in funding and timing.
Traffic Safety Capital Program | HSIP Crosswalk & Sign Enhancements (Formerly: "RISTARS - East Bay - Near-Term Signing, Striping, & Signal Safety Improvements") | 9607 | Statewide | 1.395 | 1.48 | 0.085 | 2018 | 2018 | Minor changes are being made to the cash flows for this line item. Overall, the budgetary change to this project is minimal.
Traffic Safety Capital Program | Intersection Safety Improvements | 9601 | Statewide | 20.7895 | 30.007 | 9.2175 | 2018 | 2018 | The Bishop Hill project is being added to this line item. The Bishop Hill project consists of safety improvements including lane widening, the installation of a left-hand turn lane, and the placement of new guardrail at the intersection of Bishop Hill Road and Route 6 (Hartford Avenue) in Johnston. In addition, the old funding from TIPID 1541 in FFYs 22-24 is being added to this line item. In FFY18 and 19, additional funding is being added for PTS ID 0025Z. Finally, funding is increasing in FFY20 for currently future projects.
Traffic Safety Capital Program | Limited Access Roadway Guide Sign Replacement | 1432 | Statewide | 14.5 | 15.23 | 0.73 | 2021 | 2020 | Minor changes are being made to the cash flow and timing for this line item.
Traffic Safety Capital Program | Office of Traffic Safety (including State Traffic Commission support)-3850112 (Formerly: "State Traffic Commission Support") | 1431 | Statewide | 4.5 | 4.5 | 0 | 2018 | 2018 | Updating the project description and name to reflect the usage of this line item. Minor changes are being made to the cash flows of this line item. Overall, there is no budgetary change for this line item.
Traffic Safety Capital Program | RISP Weight Enforcement | TBDTS1R | Statewide | 0 | 5.4 | 5.4 | N/A | 2019 | This line item supports the Rhode Island State Police (RISP) in their enforcement of commercial motor vehicle weight restrictions. This line item is supported by state funds, as directed by a MOU.
Traffic Safety Capital Program | Roadway Departure Mitigation (Formerly: "Roadway Departure Mitigation - Non-Freeway Roadside Improvements") | 9609 | Statewide | 13.661 | 33.036 | 19.375 | 2018 | 2018 | The addition of funding to this line item includes $2.76M in August Redistribution funding from FFY18. In addition, funding is being added to this line item in other years to service the state's roadway departure mitigation needs.
Traffic Safety Capital Program | Roadway Departure Mitigation - Horizontal Curve Enhancements | 9608 | Statewide | 0.9 | 1.8 | 0.9 | 2018 | 2018 | Adding in $0.9M from August Redistribution in 2018.
Traffic Safety Capital Program | State Traffic Commission Improvements | 9605 | Statewide | 17.61 | 22.76 | 5.15 | 2018 | 2018 | The addition of funding to this line item includes $2.90M in August Redistribution funding from FFY18. In addition, funding is being added to this line item in other years to service the anticipated needs of State Traffic Commission Improvement projects.
Traffic Safety Capital Program | Traffic Signal Optimization | 9602 | Statewide | 0.075 | 0 | -0.075 | 2018 | N/A | This line item has been removed from the STIP.
Traffic Safety Capital Program | Wrong Way Driving Mitigation (Formerly: "Wrong Way Driving Mitigation - Geometric Improvements to Ramp Facilities") | 9612 | Statewide | 3.913 | 3.913 | 0 | 2018 | 2018 | The cash flow supporting this line item is being adjusted to reflect the obligation of funds in FFY18 and funding needs in FFY19.
Transit Operations - RIDOT | AMTRAK Access Fee | 7101 | Statewide | 26.4 | 24.822 | -1.578 | 2018 | 2018 | Altering funding to reflect project needs.
Transit Operations - RIDOT | Commuter Rail Liability Insurance (Formerly: "RI Liability Insurance") | 7102 | Statewide | 18.3405 | 18.4622 | 0.1217 | 2018 | 2018 | Increasing to match insurance rate increases.
Transit Operations - RIDOT | Commuter Rail Marketing | 7104 | Statewide | 1 | 0 | -1 | 2018 | N/A | The funding for this line item is being consolidated into TIPID 7105
Transit Operations - RIDOT | MBTA Operations (Capital for Operations) | 7107 | Statewide | 20 | 15.25 | -4.75 | 2018 | 2018 | RIDOT has determined that the funding for this line item does not need to be programmed in FFY20 or FFY21.
Transit Operations - RIDOT | Other Operating Expenses | 7105 | Statewide | 1 | 4 | 3 | 2018 | 2018 | Funding from other line items is being consolidated into this line item to more closely resemble the FTA granting format.
Transportation Alternatives | ADA Plan Project Implementation | 9011 | Statewide | 1.7 | 1.72 | 0.02 | 2019 | 2019 | Project funding increased to allow RIDOT to meet federal requirements of ADA Transition Plan.
Transportation Alternatives | GEB Bicycle Improvements Contingency Account | 1492 | Statewide | 4.96 | 3.69 | -1.27 | 2018 | 2019 | 2018 funding has been zeroed out as FFY18 has concluded. $0.04M is being added to this line item in FFY19 from earmark funds. 2021 funding source shifted to state funding to be more flexible in aiding projects in need.
Transportation Alternatives | Recreational Trails Program | 5253 | Statewide | 5.787 | 10.795 | 5.008 | 2018 | 2018 | The funding for this line item is being adjusted to include $516k earmark in FFY2019 within OtherFederal line, along with match in RICAPfunds. In addition, the funding for this line item is increasing over ten years to include required recreational trails federal funding set-aside on an annual basis, plus state match.
Transportation Alternatives | Safe Routes to School Contingency, Bike Safety, and State of Good Repair Funding (Formerly: "Safe Routes to School Contingency") | 1495 | Statewide | 7.48 | 3.89 | -3.59 | 2018 | 2019 | This line item has been reduced to service the needs of existing SRTS projects, including TIPID 5267. Future funds will be transferred as necessary to meet the needs of other SRTS projects.
Transportation Alternatives | TAP Program General Contingency Account | 1493 | Statewide | 16.821 | 4.71 | -12.111 | 2026 | 2021 | $0.4M in RICAPBike funds are being added to this line item beginning in FFY21. This line item will be accessed as needed to support needs of ongoing TAP projects. The outyear funding for this line item has been reduced to support projects included in the TAP.
Transportation Alternatives | Urban bike route markings & amenities (Green Economy Bond) | 5023 | Statewide | 0.3 | 0.3 | 0 | 2018 | 2022 | This project was incorrectly identified as a Green Economy Bond funding recipient in FFY18. It is being shifted to start in 2022, funded with non-GEB funds.
Bridge Capital Program | Bridge Group 15C | 225 | Tiverton | 0.54 | 0.54 | 0 | 2019 | 2023 | RIDOT has deteremined that this bridge group should be delayed 4 years to address readiness issues. The budget is remaining unchanged, but the project will begin in the outyears as opposed to the constrained period.
Bridge Capital Program | Bridge Group 44_H | TBD44H | Tiverton | 0 | 1.6 | 1.6 | N/A | 2021 | Bridge #029201 is an historic bridge in need of independent coordination and construction. Added 029201
Pavement Capital Program | Bridgeport Rd & Highland Rd | 1404 | Tiverton | 1.8 | 2.22 | 0.42 | 2020 | 2022 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | East Rd (Rt 179 to Rt 81) | 1403 | Tiverton | 4.3 | 4.3 | 0 | 2022 | 2022 | Minor changes to funding sources.
Pavement Capital Program | Fish Rd (Rt 177 to Mass. S/L) | 1402 | Tiverton | 2.8 | 3.52 | 0.72 | 2023 | 2023 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 24 (Rt 138 to Massachusetts S/L) | 1287 | Tiverton | 5.5 | 5.75 | 0.25 | 2025 | 2025 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 77, Main Rd (Central Ave to Fairfield Ave) | 1405 | Tiverton | 3.6 | 5.82 | 2.22 | 2023 | 2024 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | Sousa Road (Rt 138/Main Rd to Fish Rd) | 9506 | Tiverton | 1.04 | 1.04 | 0 | 2024 | 2024 | Minor changes to funding sources.
Traffic Safety Capital Program | Intersection Safety Improvements to Canning Boulevard at Stafford Road Tiverton - Roundabout | 1484 | Tiverton | 1.8 | 0.785 | -1.015 | 2018 | 2018 | Finance data shows $0.785M of STBG funds obligated in FFY2018, in addition to combined $1.168M in prior years. Adjusting the cash flow to reflect this reality.
Pavement Capital Program | Birch Swamp Rd and Schoolhouse Rd (Market St to Long Ln) | 1406 | Warren | 1.2 | 3.42 | 2.22 | 2024 | 2024 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Improvements to Main St (Warren Br. to Child St.) (Formerly: "Rt 114, Main St (Warren Bridge to Child St)") | 1408 | Warren | 0.7 | 0.805 | 0.105 | 2021 | 2022 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | RT 136, Market St/Kickemuit St/Metacom Ave/Arlington Ave (Bristol T/L to Massachusetts S/L) and Market St from RT 114 to RT 136. | 1409 | Warren | 7.2 | 8.95 | 1.75 | 2023 | 2024 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | Vernon St (Rt 114 to Rt 136) | 1407 | Warren | 1.4 | 1.4 | 0 | 2024 | 2024 | Minor changes to funding sources.
Transportation Alternatives | East Bay Bike Path Extension (Warren Bike Path) | 5271 | Warren | 2 | 2 | 0 | 2022 | 2022 | Cash flow maintained.
Transportation Alternatives | Safe Routes to School Infrastructure Improvements for Hugh Cole Elementary School and Kickemuit Middle School | 5267 | Warren | 1.36 | 4.94 | 3.58 | 2018 | 2019 | Project funding increased due to utilization of contingency.
Bridge Capital Program | *REMOVED* Bridge Group 23A (Formerly: "Bridge Group 23A") | 249 | Warwick | 11.51 | 0 | -11.51 | 2021 | N/A | Independent funding is no longer required for these two bridges as a group, so this line item is being eliminated from the bridge capital program. Bridge 035021 is owned and operated by RIAC, while bridge 007901 is being moved to Bridge Group 23C. Removed 007901 Removed 035021
Bridge Capital Program | *REMOVED* Bridge Group 23_R (Formerly: "Bridge Group 23_R") | 248 | Warwick | 1.45 | 0 | -1.45 | 2020 | N/A | This bridge is being handled in Statewide Bridge Repairs Contract 4. It no longer requires funding as an independent bridge group. The project is therefore being removed from the Bridge Capital Program.
Bridge Capital Program | Bridge Group 05TC (C) | 74 | Warwick | 10.88 | 20.5 | 9.62 | 2018 | 2018 | This project is fully funded by the 2016 GARVEE issuance, which was shown in a prior STIP as a lump sum. The project funding that is now being shown reflects the actual cash flow needed to support the project as bid.
Bridge Capital Program | Bridge Group 23B | 250 | Warwick | 5.06 | 6 | 0.94 | 2020 | 2019 | The funding for this line item is being altered to meet the needs of the project. In addition, the project is being accelerated due to readiness.
Bridge Capital Program | Bridge Group 23C | 251 | Warwick | 1.1 | 1.3 | 0.2 | 2020 | 2020 | Bridge #007901 is being added to this bridge group from Bridge Group 23A, along with the funding required to support the needs of this project. Added 007901
Bridge Capital Program | Bridge Group 59B | 91 | Warwick | 4.3 | 5.72 | 1.42 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project.
Bridge Capital Program | Bridge Group 67 | 62 | Warwick | 1.2 | 2.51 | 1.31 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Airport Connector (I-95 to TF Green Airport) | 1294 | Warwick | 2.3 | 2.6 | 0.3 | 2025 | 2025 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | I-95 Contract-1 (Rt 2 to Rt 113) | 1267 | Warwick | 3.3 | 0 | -3.3 | 2019 | N/A | This line item was consolidated with TIP ID 1268 and completed as a singled contract. This line item may therefore be removed from the TIP.
Pavement Capital Program | I-95 Contracts 1 and 2 (Rt 2 to Service Ave) (Formerly: "I-95 Contract-2 (Rt 113 to Service Ave)") | 1268 | Warwick | 8.1 | 7.254 | -0.846 | 2018 | 2018 | This line item was consolidated with the fomer TIP ID 1267 and executed as a single contract.
Pavement Capital Program | Improvements to Rt. 2 (Rt. 401 to Rt. 113) | 5273 | Warwick | 4.9 | 12 | 7.1 | 2020 | 2023 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this project is increasing to more accurately reflect the estimated costs to complete work outlined in this line item.
Pavement Capital Program | Rt 113, East Ave (Rt 2 to Rt 5) | 1412 | Warwick | 2.7 | 5.22 | 2.52 | 2024 | 2025 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | Rt 113, Main Ave (Rt 5 to Rt 117) | 1413 | Warwick | 4.7 | 6.62 | 1.92 | 2023 | 2026 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | Rt 117, Centerville Road (Quaker Lane to Diamond Hill Rd) | 9536 | Warwick | 5.411 | 0.54 | -4.871 | 2026 | 2027 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. Additional funding may be added to this project in the years beyond the scope of the current STIP (2028 or later).
Pavement Capital Program | Rt 117, West Shore Rd (Long St to Oakland Beach Ave) | 1410 | Warwick | 4.4 | 7.87 | 3.47 | 2025 | 2025 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 1A/Post Rd (Rt 1/Elmwood Ave to Rt 117/Warwick Ave) | 9543 | Warwick | 6.185 | 3.4 | -2.785 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 5, Greenwich Ave (Rt. 113/Main Ave to Rt 117/Centerville Road) | 9551 | Warwick | 0.751 | 0 | -0.751 | 2027 | N/A | This project is being deferred for future planning and study. For the time being, it will be delayed beyond the endpoint of this STIP (FFY2027).
Pavement Capital Program | Rt. 117A, Warwick Ave (Sandy Lane to Airport Rd) | 9555 | Warwick | 7.828 | 0 | -7.828 | 2026 | N/A | This project is being deferred for future planning and study. For the time being, it will be delayed beyond the endpoint of this STIP (FFY2027).
Pavement Capital Program | US-1, Post Rd (Coronado to Rt 1A) | 1414 | Warwick | 3.6 | 5.6 | 2 | 2021 | 2022 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | West Shore Rd (Warwick Ave to Delwood Road) | 9565 | Warwick | 0.385 | 0.13 | -0.255 | 2027 | 2027 | The budget for this line item is being altered to meet the needs of the project.
Traffic Safety Capital Program | Interchange Safety Improvements to I-95 at Route 37 Warwick - Frontage Road | 1544 | Warwick | 9.93 | 0 | -9.93 | 2021 | N/A | The funding for this line item is being reallocated to other projects throughout the Traffic Safety Capital Program.
Transit Capital Program - RIDOT | TF Green Airport Intercity Rail Service Preliminary Engineering | TBDTFGA | Warwick | 0 | 3.5 | 3.5 | N/A | 2020 | In June 2019, RIDOT received a $2.8M CRISI grant to support this project. That funding is being added to the TIP, along with the required state match. (Project limits changes from "" to "TF Green Airport")
Bridge Capital Program | Bridge Group 95 | TBDTMM | Warwick, East Greenwich | 0 | 2.5 | 2.5 | N/A | 2019 | This line item is being created to support design and development of a potential future project to address the "missing move" at the I-95/RI-4 interchange. The funding for this line item was made available by a funding source exchange with TIP ID 1381, which is supported by Land Sale revenue. Added TBD
Pavement Capital Program | Rt 117, Centerville and Legris Ave (Rt 33 to Quaker Ln) | 1416 | Warwick, West Warwick | 1.5 | 2.1 | 0.6 | 2020 | 2022 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Bridge Capital Program | Bridge Group 57K | 194 | West Greenwich | 2.4 | 4.1 | 1.7 | 2018 | 2018 | The funding for this line item is being altered to meet the needs of the project.
Bridge Capital Program | Bridge Group 71 | 66 | West Greenwich | 17.511 | 17.511 | 0 | 2018 | 2018 | The funding sources supporting this line item are being altered to service the needs of the program.
Pavement Capital Program | Rt 33, Providence St (Tollgate Rd to East Ave) | 1417 | West Warwick | 1.95 | 1.96 | 0.01 | 2022 | 2024 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this line item is being altered to meet the estimated needs of the project.
Pavement Capital Program | 1R Improvements to Potter Hill Road (Formerly: "Potter Hill Rd (High St to Hopkinton T/L)") | 1421 | Westerly | 1.9 | 0.26 | -1.64 | 2020 | 2018 | The budget for this line item is being altered to meet the needs of the project. RIDOT has determined that this project can be completed with a reduction in funding.
Pavement Capital Program | Rt 78 (Rt 1 - Conn S/L) (Formerly: "Rt 78 (US-1 to Connecticut S/L)") | 1289 | Westerly | 5.72 | 4.6 | -1.12 | 2018 | 2018 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt. 3, High Street (Ashaway Rd. to Oak St) | 9559 | Westerly | 1.706 | 1.85 | 0.144 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | US-1, Granite St and Fanklin St (Tower St to Rt 78) | 1420 | Westerly | 2 | 2.2 | 0.2 | 2024 | 2024 | The budget for this line item is being altered to meet the needs of the project.
Transportation Alternatives | Bay Street Streetscape Improvements | 5286 | Westerly | 1.4 | 1.4 | 0 | 2018 | 2018 | Project advanced by RIDOT to construction.
Transportation Alternatives | Safe Routes to School Infrastructure Improvements for State Street Elementary School | 5285 | Westerly | 0.696 | 0.69 | -0.006 | 2018 | 2018 | RIDOT has determined that this project can be completed with a reduction in funding.
Transportation Alternatives | Westerly loop (Green Economy Bond) - Misquamicut Bike Loop | 5123 | Westerly | 0.33 | 0 | -0.33 | 2018 | N/A | Project shifted to Green Economy Bond funding provided by DEM for implementation
Bridge Capital Program | Bridge Group 26B | 220 | Woonsocket | 13.917 | 19.55 | 5.633 | 2023 | 2023 | The funding for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Rt 122, Mendon Rd (Cumberland Hill Rd to Massachusetts S/L) | 9538 | Woonsocket | 8.753 | 4.82 | -3.933 | 2026 | 2026 | The budget for this line item is being altered to meet the needs of the project.
Pavement Capital Program | Social Street (Main St. to Mass S/L) | 5312 | Woonsocket | 1.3 | 2.92 | 1.62 | 2019 | 2024 | RIDOT is delaying this project based on evaluation of pavement conditions and funding availability. In addition, the funding for this project is increasing to more accurately reflect the estimated costs to complete work outlined in this line item.
Transportation Alternatives | Blackstone River Bikeway - Segment 8A | 5293 | Woonsocket | 4.04 | 4.04 | 0 | 2019 | 2020 | Project resequenced due to environmental permitting and readiness issues.
Transportation Alternatives | Blackstone River Bikeway - Segment 8B-1 | 5318 | Woonsocket | 2.45 | 2.45 | 0 | 2018 | 2018 | Project advanced by RIDOT to construction.
Transportation Alternatives | Blackstone River Bikeway - Segment 8B-2 | 5319 | Woonsocket | 2.64 | 2.64 | -1e-08 | 2023 | 2020 | Advanced due to project readiness.
Transportation Alternatives | Main Street Improvements | 5309 | Woonsocket | 5 | 5 | 0 | 2019 | 2019 | Minor changes are being made to the cash flows for this line item. Overall, no budgetary change for this line item.
Transportation Alternatives | Safe Routes to School Infrastructure Improvements for Citizens and Pothier Elementary Schools | 5294 | Woonsocket | 0.3125 | 0.32 | 0.0075 | 2018 | 2018 | Project proceeding to construction bid advertising. Project PTSID is being updated here as well.
Transportation Alternatives | Woonsocket River Landing | 5307 | Woonsocket | 0.39 | 0 | -0.39 | 2023 | N/A | Project deferred for cost and readiness review by Statewide Planning and RIDOT.